## Start Here
IGU Design Changes - Master Sheet
Consolidated from the Mobbin deep-dive (10 benchmark apps) + a direct read of IGU's code. One row = one design change.
How to use
Work from the "Design Changes" tab. It has an autofilter - sort by Priority to plan a sprint, or filter by Area to focus one surface.
Use the Status column to track progress (e.g. Todo / In progress / Done / Won't do).
Priorities reflect design-leverage-per-effort, not absolute importance. They are recommendations - you own the final call.
Most P0s are M-effort copy/layout/data-viz work, not rebuilds: IGU's architecture is already sound.
Legend
Priority | P0 = highest leverage (around launch) P1 = soon after P2 = polish / nice-to-have
Effort | S = hours M = a day or two L = multi-day / structural
Top 10 highest-leverage moves
1. CC2 - Plain-language interpretation on every metric (P0)
2. CC1 - One metric-card data-viz standard across all charts (P0)
3. RO1 / CO5 - Coach roster: make at-risk loud + add saved Views with counts (P0/P1)
4. WK2 / WK3 - Auto-start rest timer + bulletproof workout resume (P0)
5. NU1 - Weight trend vs raw scatter in nutrition (P0)
6. CO1 - Coach dashboard: one "needs you now" number (P0)
7. HX1 - Exercise detail = trend + PR + history (P0)
8. NU3 - Weekly check-in: "here's your new target and why" (P0)
9. CC3 / CC4 - Mobile nav unread badges + drop the "More" overflow (P1)
10. NU6 / PUB1 - Shareable phase-summary card + a sharp landing hero (P1/P2) for launch growth
Explicitly OUT of scope
Plate calculator (per your instruction). Food-diary / barcode / food-search logging (IGU is adherence/target-based, not a food log).
Reference apps (Mobbin)
App | Best for + link
Hevy | Workout logging, set types, timers, history, calendar
MacroFactor | Adaptive nutrition: trend -> adjusted target, check-ins
WHOOP | Data-viz: hero metric + trend + drivers; reports; share
Oura | Insight-card home, score rings + interpretation, trends
Future | 1:1 coach-client: selection, profiles, scheduling
Ladder | Team plans + messaging: coach chat, pinned, cheers, rewards
Fitbod | Onboarding quiz, library filtering by muscle/equipment
Intercom (Web) | Coach-side CRM: inbox views, three-pane, detail accordion
Centr | Content/video library, program detail, player controls
Apple Fitness | Reorderable dashboard cards, awards system

## Design Changes
ID | Area | Surface | Recommendation | Why it matters | Priority | Effort | IGU file(s) | Mobbin reference | Status
CC1 | Cross-cutting | All charts | Standardize one "metric card" pattern for every chart (label - timeframe - sparkline - hero value - delta - avg) | One learned visual pattern; instant cross-surface consistency | P0 | M | WeightProgressGraph, BodyFatProgressGraph, VolumeChart, EnhancedProgressTracker, ui/chart.tsx | Oura data screens; WHOOP Insights | Shipped — feat/cc1-cc2-metric-card (PR-A; adopted PR-B/C/D) + deployed to prod 2026-06-18
CC2 | Cross-cutting | All metrics | Pair every number with a one-sentence plain-language interpretation | Biggest perceived-quality jump for least effort; data already in state | P0 | M | dashboards (client/coach), nutrition/NutritionPhaseCard | Oura; WHOOP Insights | Shipped — PR-B/C — NutritionPhaseCard, WeeklyProgressCard, coach overview + deployed to prod 2026-06-18
CC3 | Cross-cutting | Mobile nav | Add unread-count badge support to bottom nav items | Pulls coaches/clients back into messages | P1 | S | layouts/MobileBottomNav.tsx | Ladder Coach chat | SHIPPED + COWORK-VERIFIED ON PROD 2026-07-05 (commit 2ea3c17). formatUnreadBadge extracted to src/lib/unread.ts (shared w/ ClientSidebar); MobileBottomNav gains optional badge (visible-item pill + More-button dot + overflow-item badge, all guarded=additive); App.tsx MobileBottomNavClient injects useUnreadMessageCount(user.id) onto the /messages item. Verified as +online mobile viewport with a seeded unread: More-button red dot + overflow Messages "1" badge matching the RPC count; cleared to no-dot/no-badge on cleanup (count 0). Coach/admin docks unchanged (no messages destination). NOTE: deploy briefly served intermediate bundles (CDN mid-deploy) before stabilizing on index-5d0cjs_P -- hard-reload before trusting.
CC4 | Cross-cutting | Mobile nav | Use 5 fixed tabs where a role has 5 destinations (drop the "More" overflow); bump active label to 11px | Overflow hides primary destinations behind a tap | P1 | S | MobileBottomNav.tsx, Client/Coach/AdminMobileNavGlobal | Hevy / Future / Oura tab bars | SHIPPED + COWORK-VERIFIED ON PROD 2026-07-05 (commit b5c4592, bundle index-DHL8mwnp). Client dock = 5 fixed tabs (Home/Nutrition/Workouts/Learn/Messages), no More overflow; Messages tab shows the CC3 unread badge on its icon (aria-label N unread). Verified +online mobile 375px + 320px (iPhone SE) -- 5 tabs flex evenly, no cramping, labels readable. Coach/admin docks unchanged (slice to <=4, tight path never triggers). maxVisible=5 on client dock + tight=len>=5 flex-1 min-w-0 + badge re-anchored to icon wrapper. CDN served prior bundle (DHCwaafi) on first check, propagated on retry.
CC5 | Cross-cutting | Theme | Define semantic status-color tokens (ontrack / attention / risk / neutral); route all Badges and dots through them | Cross-surface status consistency from one source of truth | P1 | S | index.css, lib/statusUtils.ts | WHOOP / Oura status colour language | Shipped — PR-A — status + chart tokens + Tailwind safelist; fixed latent --chart-1/--warning bug + deployed to prod 2026-06-18
CC6 | Cross-cutting | Loading | Replace full-page spinners on content surfaces with layout-shaped skeletons | Removes blank-then-pop jank; feels faster on the Capacitor WebView | P1 | S | ui/loading-skeleton.tsx; Dashboard.tsx, CoachDashboard.tsx | Fitbod/Hevy layout-shaped skeletons (sheet orig) | PARTIAL->WORSE (CC 2026-07-12): coach-side 53 files Loader2/spinner vs 4 Skeleton; client-side 9. Coach surface spinner-only. Full-page: CoachDashboardOverview:271, DietitianDashboardOverview:257, CoachMyClientsPage:1038, CoachSessions:408, ClientOverviewPanel:209. BUNDLE w/ CC10 error-sweep -> one pass = skeleton + error branch per surface. // (prior) KEEP 2026-07-12 (still P1) -- shape skeletons to real components (MetricCard grids/roster rows). SPEC: DESIGN_UPGRADE_SPECS_BATCH2_2026-07-12.md.
CC7 | Cross-cutting | Overviews | Establish one-hero + ranked-stack hierarchy; visually quiet the secondary cards | When every card is equal weight, nothing leads | P1 | M | client/ClientDashboardLayout.tsx, coach/CoachDashboardOverview.tsx | Oura / Future home | BUILT (verified 2026-07-05 recon): NewClientOverview.tsx one-hero (TodaysWorkoutHero) + ranked single-column stack + right rail; 2-col grids gone (PR #178).
CC8 | Cross-cutting | Empty states | Audit that every list/history uses EmptyState; add optional illustration slot for high-traffic empties | Coverage + perceived quality at near-zero cost | P2 | S | ui/empty-state.tsx | Fitbod/Hevy empty states (orig) | UPGRADE 2026-07-12 -- re-spec to current bar: EmptyState primitive is house style now; scope = coverage audit + tasteful mono-icon/illustration slot, flat aesthetic. Merge w/ RO5. See DESIGN_BACKLOG_RECONCILIATION_2026-07-12.md SPEC: DESIGN_UPGRADE_SPECS_BATCH2_2026-07-12.md.
CL1 | Client | Dashboard | Apply one-hero (TodaysWorkoutHero) + ranked stack; demote billing/plan to a quiet "Account" group | Information scent; reduce the card wall | P1 | M | ClientDashboardLayout.tsx, client/*Card.tsx | Future / Oura home | Shipped + LIVE-VERIFIED (2026-06-23) -- merged main PR #178 (0f1b7b6), live on prod. Restructured the ACTIVE client dashboard overview in NewClientOverview.tsx (the card-grid OverviewSection in ClientDashboardLayout is orphaned dead code, untouched). Verified live via a team client (Hasan, desktop, /dashboard): interrupts (AlertsCard 'Missing Weight Logs') -> Today's Workout hero -> single-column ranked stack (Daily Targets -> This Week -> Adherence -> Your Coach -> My Care Team) -> QuickActionsGrid (Weekly Check-In / Nutrition / Exercise Library) -> quiet 'Account' group (border-t + muted heading) with PlanBillingCard demoted to the bottom. Both 2-col grids gone; all cards present once. tsc+build clean. Mobile reads the same single column (grids dropped); explicit phone pass optional.
CL2 | Client | Dashboard | Give WeeklyProgressCard / NutritionTargetsCard the metric-card + interpretation treatment | Quality + at-a-glance clarity | P0 | M | client/WeeklyProgressCard.tsx, NutritionTargetsCard.tsx | Oura; MacroFactor Goal progress | Shipped — merged main PR #166 (ca6e822), deploys to prod via Vercel. WeeklyProgressCard (PR-B) + NutritionTargetsCard now CC1/CC2: per-macro % + interpretMacroTargets() line. Visual confirm at post-deploy smoke.
CL3 | Client | Dashboard | Make LogTodayCard the lowest-friction object: inline numeric entry, no navigation | Drives the daily-habit loop | P1 | S | client/LogTodayCard.tsx | MacroFactor Adding a weight data | BUILT (verified 2026-07-05 recon): LogTodayCard.tsx:188-213 inline weight+steps Input + inline Log buttons, no navigation.
CL4 | Client | Dashboard | Turn pending / medical-review / approval / grace states into proper holding states (single action + illustration) | Replace text-heavy status branches with clear next steps | P1 | M | ClientDashboardLayout.tsx state machine | Fitbod holding screens | BUILT (verified 2026-07-05 recon): ClientDashboardLayout.tsx:217-270 holding states (needs_medical_review / pending_coach_approval / pending_payment) as focused single-action Alert UI.
CL5 | Client | Dashboard | Add a lightweight streak / consistency indicator near the hero | Retention; keep framing gentle/positive | P2 | M | client/ dashboard | timespent Arcs gentle week-dots (mobbin.com/screens/9cc7a829-7e52-4fba-a224-d18fba39c85e); Me+ (…/68f3faa7). NOT QUITTR flame-streak (anti-pattern) | UPGRADE 2026-07-12 -- re-spec to current bar: mono counter, GENTLE framing (no streak-pressure, wellbeing). Overlaps AD2 -- consolidate. Ground in Oura/Ladder. See recon 2026-07-12.md SPEC: DESIGN_UPGRADE_SPECS_BATCH2_2026-07-12.md.
CO1 | Coach | Dashboard | Lead with one "needs you now" number (overdue check-ins + approvals + unread); demote the 8 metric tiles to a secondary row | Triage scent: what to do next, first | P0 | M | coach/CoachDashboardOverview.tsx | WHOOP Overview; Intercom Inbox | Shipped + deployed — feat/co1-attention-headline merged main/prod (eeda317). NeedsAttentionAlerts banner + useCoachRosterAttention as single source on CoachDashboardOverview; roster-attention RPC adds adjustments_pending + most_overdue_days + per-bucket IDs (migrations 20260617200928/200929/211721 + 20260619000718). Verified at HEAD d428bf2.
CO2 | Coach | Dashboard | Add direction + interpretation to the 8 metrics (e.g. "3 check-ins due - 1 overdue 9d") | Makes each number decision-useful | P0 | S | coach/CoachDashboardOverview.tsx | WHOOP / Oura | SHIPPED + LIVE-VERIFIED 2026-06-26 — metric cards carry interpretation/direction lines (e.g. "1 check-in due — 1 is 11d overdue", "7 of 7 clients active"); token pass folded into DS1 (mono numbers, flat cards). No fabricated deltas.
CO3 | Coach | Dashboard | Restyle ClientActivityFeed as a real feed (avatars + relative time) - the emotional core | Engagement: who trained / logged / is slipping | P1 | M | coach/ClientActivityFeed.tsx | Ladder Workout activity | Largely done — ClientActivityFeed already an avatar+relative-time feed. Polish only: add check-in/message types + team_id scoping. P2. // Reviewed 2026-07-12 CC pass: leave as largely-done.
CO4 | Coach | Dashboard | Show capacity as a filled gauge (e.g. 18/25 clients) | Read load at a glance | P2 | S | coach/EnhancedCapacityCard.tsx | Oura Activity Goal arc gauge (mobbin.com/screens/c8eceb02-6db4-4cfd-9a46-e1ed8fa90e0a) | UPGRADE 2026-07-12 -- re-spec EnhancedCapacityCard as MetricCard-family filled gauge (18/25) in current tokens. See recon 2026-07-12.md SPEC: DESIGN_UPGRADE_SPECS_BATCH2_2026-07-12.md.
CO5 | Coach | Dashboard / roster | Add saved "Views" with live counts in the sidebar (Action needed 3, Drifting 2) | Counts are the best next-action driver | P1 | M | coach/CoachDashboardLayout.tsx, rosters | Intercom Inbox views | Shipped + deployed - get_coach_roster_attention() RPC + sidebar badge (PR-2/FU3), merged main + prod 2026-06-18; dietitian roster live-verified
CO6 | Coach | Client detail | Desktop three-pane: roster list -> client detail -> context panel (collapses to push-nav on mobile) | Keeps coach in flow while triaging many clients | P1 | L | coach/CoachClientDetail.tsx, rosters | Intercom Inbox | Shipped + LIVE-VERIFIED (2026-06-23) -- merged main PR #183 (57e7720), live on prod. Coach client view is now a MASTER-DETAIL workspace inside the coach shell (new CoachClientsWorkspace): the CoachSidebar global nav is preserved (no more dead-end page), a persistent compact roster on the left (reuses the roster hooks -- name + plan + adherence/check-ins + alert dots + urgency rail, search + sort, 'Full queue' -> ?view=queue keeps Pending/At-Risk/approvals reachable), and the selected client's detail (ClientOverviewPanel, extracted from the now-deleted standalone CoachClientOverview) in the right pane. App.tsx repoints /coach/clients/:id into CoachDashboard (shell); CoachDashboard derives section from the path. Verified live via coach session (desktop): clicking a client swaps the RIGHT PANE CLIENT-SIDE (no reload), master stays, row highlights, sidebar persists, the 8 section tabs work; 'Select a client' empty state when none selected; check-ins X/3 + tone + alert dots populate from the RO Phase 2 RPC. tsc+build+eslint clean. KNOWN FOLLOW-UP (separate ticket): the detail's Overview 'Last weigh-in' card + Nutrition trend still read weight_logs client-side (coach RLS) -> 'No weigh-ins yet' even with logs; needs a coach-scoped read like get_coach_roster_stats. MOBILE pending a phone pass (drawer master + the two 'Clients' buttons + lg pane-height calc(100vh-12rem) nudge). Pairs with CO7 (per-tab accordion) if desired -- separate.
CO7 | Coach | Client detail | Collapsible accordion sections (Profile / Program / Nutrition phase / Activity / Notes) | Jump to the needed section without scrolling a monolith | P1 | M | coach/CoachClientDetail.tsx, client-overview/* | Intercom context panel | SUPERSEDED (verified 2026-07-05 recon): client overview uses horizontal section TABS (ClientOverviewNav/RD1), not an accordion. Board item moot.
CO8 | Coach | Reports | Reports view: date-range filter + metric-card grid | Consistent coach/admin analytics | P2 | M | coach/CoachDashboardOverview.tsx, admin/AdminMetricsCards.tsx | IGU CC1 MetricCard (house standard); Intercom Reports (orig) | UPGRADE 2026-07-12 -- now a MetricCard grid (CC1 house style) + date-range filter; consistent coach/admin analytics. See recon 2026-07-12.md SPEC: DESIGN_UPGRADE_SPECS_BATCH2_2026-07-12.md.
RO1 | Coach | My Clients roster | Make at-risk loud: risk colour + left status rail; the at-risk client should be findable in under 1s | Core coach workflow is triage | P0 | S | coach/CoachMyClientsPage.tsx, DietitianMyClientsPage.tsx | CRM triage rows (Intercom/Front) | Shipped + deployed - PR-1/FU1 (rail + drift chip + at-risk-first sort + token migration), merged main + pushed to prod 2026-06-18; live-verified
RO2 | Coach | My Clients roster | One scannable status line per row (name - phase - last weigh-in - warning) with consistent column rhythm | Scannability; all the data already exists | P1 | M | rosters | Superhuman / Front list rows | Phase 1 SHIPPED + LIVE-VERIFIED (2026-06-23) -- merged main PR #181 (a604aea), live on prod. Coach My Clients roster redesigned (CoachMyClientsPage.tsx): needs-attention strip on top (jump chips from get_coach_roster_attention tiles/client_ids + awaitingPayment count; zero-count muted) + ACTIVE-FIRST reorder (action sections moved below, collapse-when-empty) + scannable two-line row (rail · name · plan / status · adherence · check-ins · last weigh-in, sm:grid-cols-4 aligned columns) + consolidated alert cluster (check-in-overdue / payment / adjustment from client_ids + unread + deload; icons only when flagged). Verified live via coach test session (4 wired test clients): strip shows '1 check-ins overdue · 9d' (seeded +hybrid quiet client) and that row shows the Clock alert icon; active roster leads; aligned columns render. tsc+build+eslint clean. PHASE 1 LIMITATION (RLS, confirmed live): the row's 'Last weigh-in' reads weight_logs CLIENT-SIDE, which coach RLS hides, so it shows 'No check-in' for ALL rows (even +online which has 9 logs). The strip's overdue count is correct because it comes from the SECURITY DEFINER RPC. => PHASE 2 RPC must feed last-weigh-in + adherence + check-ins X/3 (not just adherence). PHASE 2 PENDING: get_coach_roster_stats() / useCoachRosterStats() for adherence % + weekly check-ins + no-program alert + adherence sort -- own branch/PR per docs/RO-Coach-Roster-Redesign-Spec.md. ¦¦ PHASE 2 LIVE-VERIFIED (2026-06-23): get_coach_roster_stats() applied to prod (RO Phase 2 PR #182 frontend merged; function applied via MCP raw SQL -- SECURITY DEFINER, anon revoked, authenticated granted; a later supabase db push registers the merged migration cleanly). Roster + the CO6 master now show real check-ins X/3 + RPC-fed last-weigh-in (fixes the Phase-1 RLS 'No check-in') + no-program/alert dots; adherence shows '--' until adherence_logs/weekly_progress adherence data exists for these clients. Confirmed live in the coach session.
RO3 | Coach | My Clients roster | Add a sort control (by drift / check-in due / name) alongside search + filter | Triage is sort-first | P1 | S | rosters | CRM inboxes | SHIPPED (RO Phase 1, PR #181 a604aea, live + verified 2026-06-23) -- added 'Check-in due' sort (days_since_check_in desc, nulls last) alongside At-risk-first + Name, beside the existing search + plan filter. Adherence sort deferred to RO Phase 2 (needs the stats RPC). Adherence sort now ACTIVE (RO Phase 2 live).
RO4 | Coach | My Clients roster | Unify the training vs nutrition roster visual language | One consistent pattern for dual-hat coaches | P1 | M | CoachMyClientsPage.tsx vs DietitianMyClientsPage.tsx | Internal consistency | BUILT (verified 2026-07-05 recon): CoachMyClientsPage + DietitianMyClientsPage share the same Card/Badge/Button roster language.
RO5 | Coach | My Clients roster | Satisfying zero/empty states ("No clients need attention - nice") | Moment of delight instead of a blank section | P2 | S | rosters + ui/empty-state.tsx | EmptyState primitive + Fitbod/Hevy | UPGRADE 2026-07-12 -- merge w/ CC8; flat/mono empty state "No clients need attention -- nice". See recon 2026-07-12.md SPEC: DESIGN_UPGRADE_SPECS_BATCH2_2026-07-12.md.
WK1 | Workout | Logging | Set-row tap-to-complete checkmark with a lock state; review tap targets/feedback | Core logging feel | P1 | M | client/WorkoutSessionV2.tsx | Hevy Logging a workout | Superseded — tap-to-complete checkmark + lock state live in WorkoutSessionV2 (verified 2026-07-04); only tap-target polish remains
WK2 | Workout | Logging | Auto-start rest timer on set completion; persistent sticky countdown; evaluate Live Activity on Capacitor | Gym reality; rest is already stored in seconds | P1 | M | client/WorkoutSessionV2.tsx | Hevy timers; WHOOP/Apple Live Activity | SHIPPED (commit 7b6be79, "Workout logging A1"): RestTimer re-anchored to wall-clock end time (endAt=Date.now()+duration*1000; every 250ms tick recomputes remaining from Date.now(); force-resync on visibilitychange+focus; pause/resume re-anchors endAt; firedRef single-fire). Fixes phone-lock/background drift. Working tree clean on main. Board status was stale (d428bf2 baseline predated the fix).
WK3 | Workout | Logging | Bulletproof resume / discard of an in-progress session (handle app backgrounding mid-workout) | Backgrounding mid-set is common in a gym | P2 | M | client/WorkoutSessionV2.tsx | Hevy Resuming / Discarding | Closed (P2 polish only) — verified at d428bf2: completeSet() write-through upserts each set to exercise_set_logs (survives reload/resume); navigate-away-loses-log already fixed. Remaining: persist unchecked drafts + resume cue (P2).
WK4 | Workout | Logging | Show previous performance as ghost text inside the input ("80kg x 8 last time") | Target visible at the moment of entry | P1 | S | client/WorkoutSessionV2.tsx | Hevy set rows | SHIPPED (commit 7b6be79, "Workout logging A1"): ghost placeholders inside the set inputs show previous performance -- Weight placeholder = prefillWeightKg ?? historySet.weight; Reps = historySet.reps; RIR/RPE = historySet value (WorkoutSessionV2.tsx ~849-938) + fixed-height "last X" captions below each. Board status was stale (partial pre-7b6be79).
WK5 | Workout | Logging | Set-type affordance (warmup / normal / drop / failure) via chip or long-press | Clarity without clutter | P2 | S | client/WorkoutSessionV2.tsx | Hevy Editing set type | KEEP 2026-07-12 -- still valid, correctly specced. Ground in Hevy set-type chip at build.
WK6 | Workout | Logging | Share spacing/typography between the strength grid and the activity grid | Seamless switch between the two | P2 | S | client/WorkoutSessionV2.tsx | Internal | KEEP 2026-07-12 -- internal consistency, still valid.
HX1 | Workout | Exercise detail | Lead ExerciseHistory with a 1RM/volume trend (metric-card) -> PRs -> chronological set list | Progress is the whole point of the screen | P0 | M | client/ExerciseHistory.tsx | Hevy Exercise detail (summary) | Re-slice SHIPPED + LIVE-VERIFIED 2026-07-05 (commit 93fb9e6): Estimated-1RM (Epley) replaced with actual logged rep-maxes -- "Best load @ N reps" trend + rep-bracket chips + rep-max breakdown; canonical-read migration (fixes the B1 FK-embed break on the client history surface); oneRepMax.ts deleted; interpretE1rmTrend->interpretRepMaxTrend. Original PR #167 e1RM card superseded. Spec docs/HX1_REPMAX_BUILD.md.
HX2 | Workout | Session detail | Clean read-only past-session recap card (exercises / sets / volume / duration / PRs) | Readability over a dense table | P1 | M | ClientSessions.tsx | Hevy Workout detail | BUILT (verified 2026-07-05 recon): SessionLogViewer.tsx read-only session recap (exercises/sets/load/reps/RIR/RPE), reached via calendar tap-to-recap (B5).
HX3 | Workout | Calendar | Trained days filled + tap-to-recap; dot/crown language | History scent | P1 | M | client/WorkoutCalendar.tsx | Hevy / Oura Calendar | Largely shipped — canonical calendar dots (Done/Due/Scheduled/Missed) + tap-to-recap via SessionLogViewer (B5, 2026-07-01); confirm PR-crown marker
HX4 | Workout | Exercise library | Filter chips by target muscle + equipment, category tabs, searchable list with thumbnails | Exactly what the unified exercise_library redesign needs | P1 | M | WorkoutLibrary.tsx, coach/ExerciseLibrary.tsx | Fitbod Exercises by muscle / equipment | BUILT (verified 2026-07-05 recon): learn/ExercisesTab.tsx category tabs + muscle/region/subdivision filters + search + exercise cards (exercise-library redesign).
HX5 | Workout | Analytics | Muscle / volume distribution view (optional) | High-impact coach + client artifact | P2 | L | (new) | Hevy Muscle / Body distribution | KEEP 2026-07-12 (upgrade spec at build) -- high value; reuse useMusclePlanVolume (already computes volume). Ground in Hevy muscle/body distribution.
NU1 | Nutrition | Weight graph | Show the smoothed trend line vs raw daily scatter | Trust-defining; stops clients panicking over daily fluctuation | P0 | M | nutrition/WeightProgressGraph.tsx | MacroFactor Goal progress | Shipped — PR-B — two-series (daily dots + 7d trend + dashed target), date axis + deployed to prod 2026-06-18
NU2 | Nutrition | Expenditure | Surface computed TDEE as a trend over the phase, not just a static target | Builds trust in the macro adjustments | P1 | M | calculateNutritionGoals(), nutrition/NutritionPhaseCard.tsx | MacroFactor Expenditure | KEEP-BLOCKED 2026-07-12 -- reasoning holds; revisit after food logging. // BLOCKED (verified 2026-07-07): the valuable TDEE trend = REVERSE/real TDEE (calculateReverseTDEE = avg calories consumed +- weight-change*7700/days) which needs calories-consumed data = FOOD LOGGING (deferred/FOR_LATER). Only the formula TDEE (calculateTDEE = BMR*activity) is computable now = a smooth low-insight curve as weight drops. Revisit AFTER food logging ships. Not worth building the formula-only version.
NU3 | Nutrition | Weekly check-in | Produce a clear, celebratory "here's your new target and why" moment | The core adaptive loop made legible | P1 | M | weekly_progress -> nutrition_adjustments, nutrition/ClientNutritionAdjustments.tsx | MacroFactor Checking in early / Strategy | Shipped + LIVE-VERIFIED — re-targeted onto NutritionProgress.tsx (team flow), merged main PR #169 (1823ff2), on prod. Banner verified on theigu.com with a seeded weekly_progress row (since removed): green rail, 'Your plan just updated', 1,620 kcal hero + macro ribbon + interpretAdjustment line ('down 130 kcal... -0.8% vs -1% target'). Orphaned ClientNutritionAdjustments.tsx deleted. CC5 token pass applied. First attempt (#168) was dead-mount; caught by live smoke.
NU4 | Nutrition | Weekly ribbon | Give each ribbon segment (weigh-ins / steps / check-in) a progress ring/bar + interpretation line | Glanceable "what's left this week" | P1 | S | nutrition/ClientWeeklyRibbon.tsx | Oura Activity goal; MacroFactor | SHIPPED + COWORK-VERIFIED ON PROD 2026-07-07 (commit 7b03ca7, bundle D2rUF72z). ClientWeeklyRibbon tiles now show an interpretation line under the dots bar, per count. Verified +online (0/3, 0/7, Due): Weigh-ins -> "Log your first weigh-in", Step days -> "Log steps to start", Check-in -> "Takes about 2 min". done-state shows emerald Goal met/Full week/Done this week. No data-model change.
NU5 | Nutrition | Graphs tab | Metric-card stack (weight / body-fat / adherence / steps), each tap-to-expand | One consistent card pattern | P1 | M | ClientNutrition.tsx, nutrition graphs | Oura Trends / Reports | SHIPPED + COWORK-VERIFIED ON PROD 2026-07-07 (commit 09e6ff8, bundle CTyyX0ok). ClientNutrition (/nutrition-client) trend area = 4-tile metric-card stack (Weight 82.9kg / Body fat 14.4% / Adherence 100% "On plan 1/1 weeks" / Steps 8500 ↓2400) each w/ value+delta+sparkline+interpretation; active tile primary-ringed; 4W/12W/All range kept. Tap-to-expand verified: clicking Body fat moved the ring + swapped the detail chart below (Weight Trend -> Body Fat 14.4% ↓0.3% w/ line chart); one at a time. Weight/Body-fat charts match old toggle. New NutritionMetricStack + NutritionTrendChart components + step_logs fetch. Mobile 390px = 2-up tiles, reflows, no overflow, 5-tab dock intact. Left column (hero/ribbon/log-today) unchanged. Team surface = parallel follow-up (not built). [FOLLOW-UP FIX cf3ed84 SHIPPED+VERIFIED 2026-07-07: delta chips overflowed the narrow 4-up tiles -> fixed in the shared MetricCard primitive (metric-card.tsx: value+delta row flex-wrap + min-w-0 + DeltaChip shrink-0); delta now wraps under the value in-bounds; wide consumers (HX1 etc.) unchanged. NOTE: this commit hit the Vercel missed-webhook gotcha -- needed an empty-commit re-trigger (4624048); see feedback_vercel_missed_webhook_diagnose.]
NU6 | Nutrition | Phase summary | Make PhaseSummaryReport an exportable, shareable image card | Cheapest organic-growth lever (every share = branded ad) | P2 | M | nutrition/PhaseSummaryReport.tsx | Beli recap share card (mobbin.com/screens/ac5b8c7f-dee7-478c-aad7-8c89728720b1); Spotify Wrapped (…/9cc6cdc9) | UPGRADE 2026-07-12 -- PhaseSummaryReport -> branded exportable share image, current bar (Bebas hero kcal/weight, crimson, flat, WeightChangeProof chip). Ground in WHOOP sharing. See recon 2026-07-12.md SPEC: DESIGN_UPGRADE_SPECS_BATCH2_2026-07-12.md.
MS1 | Messaging | Threads | Pinned messages: coach pins the current plan / key instruction to the top | Improves adherence; reduces repeat questions | P1 | M | messaging/CoachClientThread.tsx | Ladder Pinned messages | SHIPPED + FULLY COWORK-VERIFIED ON PROD 2026-07-05 (commit 70e73d4, migration 20260706113740, bundle index-DqFeVtf_). DB security gate PROVEN (jwt-impersonation): client->42501 "Only staff can pin messages", coach(primary)->{pinned:true}, anon->42501. COACH UI (viewing +online): PINNED section + unpin control (staff-only); clicking unpin fired the RPC -> pinned_at/pinned_by cleared in DB + section removed + message intact. CLIENT UI (+online /messages): PINNED section read-only, NO pin controls. Multiple-pins model; realtime carries the pin (client render confirmed). Seed message cleaned up (thread pristine). Pre-existing minor (NOT MS1): coach sender name shows "Someone" on the client side. CDN served CC4 bundle ~25s before MS1 propagated.
MS2 | Messaging | Threads | Surface unread on the bottom nav (see CC3) | The thread is useless if people don't know there's a message | P1 | S | MobileBottomNav.tsx, useStaffUnreadCounts | Ladder Coach chat | SHIPPED (CLIENT DOCK ONLY) 2026-07-12: badge live MobileBottomNav.tsx:15-16,90-97 + App.tsx:142-145. CC-corrected scope: coach+admin docks have NO Messages item (CoachSidebar.tsx:232-234, AdminSidebar.tsx:131-146) -> nothing to badge. Coach on mobile has no dock unread signal. Split -> new row MS5.
MS3 | Messaging | Community | Team / community channel + cheers for team plans | Retention; offloads the coach | P2 | L | (new), coach_teams | Ladder Chat / Community / Sending a cheer | KEEP 2026-07-12 -- net-new (existing coach_client/care_team messaging dont cover team-client community). Retention, big effort. Still valid.
ON1 | Onboarding | Intake | Frame intake as a quiz with a persistent progress header + Skip where optional; single-focus steps | Momentum drives completion | P1 | M | OnboardingForm.tsx, onboarding/* | Fitbod onboarding; MacroFactor Setting up a goal | KEEP 2026-07-12 -- remaining = Skip affordance on optional steps + light momentum polish. Small scope. // PARTIAL (verified 2026-07-05 recon): OnboardingForm has persistent StepIndicator + single-focus steps, but NO Skip on optional steps.
ON2 | Onboarding | Coach selection | Recommended-coach card -> list -> rich coach profile (Specialties / Certs / About / Location) | Ready template for rendering coaches_public | P1 | M | onboarding/CoachPreferenceSection.tsx, CoachProfile.tsx | Future Pro — Recommended Coaches card (mobbin.com/screens/50e21fab-5c26-4e05-a830-f99c0d1c6212) + coach profile Specialties/About (…/20fd4906) + Certified/Located (…/fc7492bc) | SHIPPED + MERGED + PROD-DEPLOYED 2026-07-12 (squash 2902a3c, PR #189, deploy dpl_3khKUfuXpviVnbKaygFzLR1f5qJc READY; +445/-46, 6 files). Onboarding coach dialog now shows Located/Certified/derived headline/specialty chips/socials + View-full-profile deep-link to /coaches/:slug + mobile Drawer <768px. Migration 20260712145922 (grants unchanged, no anon). 5 regression tests. CARRY-FWD: intro_video_url + years_experience null for both coaches (content task, not code); human click-through still pending (WaitlistGuard blocks CC). Was UPGRADE.
ON3 | Onboarding | Nutrition | Goal setup -> program customization kickoff | Feeds calculateNutritionGoals() | P2 | M | OnboardingForm.tsx, calculator/* | MacroFactor Setting up a goal / Customizing program | KEEP 2026-07-12 -- verify current onboarding nutrition-goal capture at build; likely still valid.
ST1 | Settings | Account | Grouped settings list (sections + leading icons + chevrons) | Low-effort polish that reads as "finished" | P2 | S | AccountManagement.tsx | Instagram Settings sectioned list (mobbin.com/screens/83c9dde8-a66e-4860-bfd4-dfc1c070827d); TheFork (…/048e0d20) | UPGRADE 2026-07-12 -- re-spec AccountManagement to sectioned list: mono section heads + leading icons + chevrons + ClickableCard. Ground in Hevy/Oura settings. See recon 2026-07-12.md SPEC: DESIGN_UPGRADE_SPECS_BATCH2_2026-07-12.md.
ST2 | Settings | Subscription | Calm manage/cancel flow (current plan, next billing, explicit cancel + a retention beat) | Reduce churn friction and confusion | P1 | M | SubscriptionManagement.tsx, BillingPayment.tsx | Future Canceling a membership | BUILT (verified 2026-07-05 recon): SubscriptionManagement.tsx:280-360 current plan + next_billing_date + explicit Cancel + cancel-reason textarea (retention beat).
CT1 | Content | Library | Search + filter chips (by coach, by category/equipment) + a Saved/Favourites shelf | Findability in the content/exercise library | P1 | M | WorkoutLibrary.tsx, PlaylistViewer.tsx, EducationalVideos.tsx | pliability Find-a-Session filter chips + heart-save (mobbin.com/screens/4c77a6bb-454c-482d-9f50-0b664acf0f64); Alan (…/58c27044) | KEEP 2026-07-12 -- remaining = by-coach/equipment chips + Saved/Favourites shelf. Still valid. // PARTIAL (verified 2026-07-05 recon): Learn has search + category filter, but no by-coach/equipment filter chips and no Saved/Favourites shelf. SPEC: DESIGN_UPGRADE_SPECS_BATCH2_2026-07-12.md.
CT2 | Content | Program detail | Program / workout detail pages (overview -> structure -> start) | How a client sees an assigned program | P1 | M | client_programs, client-overview/workouts/* | Centr Program details / Workout details | SHIPPED + COWORK-VERIFIED ON PROD 2026-07-07 (commit 0290a71). /client/program/detail: header (plan "Classic Series...Meso (Copy)" + Calendar back btn) + overview (Week 2 of 8 + 2 of 40 sessions done) + vertical week sections (Week 1..) of session cards (Strength/type/7 exercises/muscles/status pill Done¦Missed + Review¦Start) + muted Rest rows. Verified: Review on the Done session opened the canonical player at correct assignment=74349417&session=32dfcd7c&date=2026-06-30 (all 3 params). Entry = "View full program" button in WorkoutCalendar header (confirmed live). Status derivation (Done/Missed/Rest) correct. Dock stays visible (/client prefix covers it; not the hidden /session path) -- CC deviation from spec accepted. Not tested: empty-state (no-assignment) + mobile 2-up (low-risk). Optional phase-2 exercise-name expand not built.
CT3 | Content | Video player | Verify cast + fullscreen + audio-switch controls (keep watermark / secure access) | The expected control set; cast + fullscreen are common gaps | P2 | S | video/SecureVideoPlayer.tsx | Centr Coached workout | KEEP 2026-07-12 -- verification task on SecureVideoPlayer (cast/fullscreen/audio); keep watermark/secure access.
CT4 | Content | Articles | Clean long-form article / educational reader | If expanding written educational content | P2 | S | EducationalVideos.tsx, educational/* | Centr Article detail | UPGRADE (conditional) 2026-07-12 -- gated on expanding written content; if built apply current typographic bar (Geist body, mono section labels). See recon 2026-07-12.md
AD1 | Additions | Dashboard | Customizable / reorderable dashboard cards (strong curated default + optional reorder/hide) | Power users; refines the hierarchy rec (CC7) | P2 | M | dashboards | Apple Fitness Adding / Reordering cards | KEEP 2026-07-12 -- power-user polish, strong curated default first. Low priority.
AD2 | Additions | Engagement | Awards / achievements screen (milestones, streaks, earned dates) | Retention; keep positive and health-aligned | P2 | M | (new) | Apple Fitness Awards / Award detail | KEEP 2026-07-12 -- retention, positive/health-aligned. Consolidate scope w/ CL5 streak (avoid two overlapping engagement surfaces).
AD3 | Additions | Coach | Auto weekly digest of roster progress via the edge-function email system | Coach efficiency | P2 | L | weekly_progress, supabase/functions email | WHOOP / Oura Reports | PARTIAL (CC-corrected 2026-07-12): send-weekly-coach-digest is an ACTIVITY digest, not a PROGRESS one -- index.ts:97-117 counts exercise_set_logs>0 per client and throws magnitude away; body = Total/Active/Inactive/New stat cards. No weight trend/adherence/volume/PRs/check-ins. AD3 roster-PROGRESS ask STILL OPEN. Cron confirmed (vercel.json:4).
AD4 | Additions | Scheduling | In-app schedule-a-call with coach | Tightens the coaching loop (vs WhatsApp) | P2 | M | (new) | Future Scheduling a call with coach | KEEP 2026-07-12 -- overlaps Sessions booking (SE1); fold into that phase, not standalone. Depends on SE1 (locked: session_bookings model).
PUB1 | Public / Marketing | Landing hero | One dominant value prop + a single primary CTA; social proof above the fold; keep the status-aware CTA | First impression for July 14 public signup; conversion | P1 | M | Index.tsx hero, getHeroCtaVariant | Future / WHOOP marketing sites (Mobbin Sites) | Shipped (code) + deploy-verified -- merged main PR #175 (6d530c6), live on prod. Hero social-proof strip (new HeroSocialProof.tsx, sibling right after heroCtaRef so PUB4's IntersectionObserver bounds are untouched): founding-cohort pill (Star icon; FOUNDING_DEFAULT shown by default; CMS-overridable via homepage/social_proof.founding_line; hideable via founding_enabled='false') + a dormant 3-cell stats row where each cell renders only when its stat{n}_value is set; component returns null when nothing to show. No live DB read (pre-launch numbers are 1 coach/0 testimonials/0 paying -- numbers come only from CMS values). tsc+build clean, diff matches spec exactly. LIVE ANON SMOKE DEFERRED: landing '/' is unreachable while waitlist is ON (anon -> /waitlist, logged-in -> role home) -- confirmed via the main vercel.app alias redirecting anon to /waitlist. Self-verifies at launch (waitlist off); or preview now by toggling waitlist off in an incognito window. Content to-do (Hasan): founding line is live by default; populate homepage/social_proof stat rows in admin as real numbers/testimonials arrive (keys in docs/PUB1-Hero-Social-Proof-Spec.md).
PUB2 | Public / Marketing | Pricing / Services | Make plan differences scannable; highlight one recommended plan; clear CTA per card | Decision clarity drives signup | P1 | M | Services.tsx, ServiceCard.tsx, marketing/ComparisonTable.tsx | SaaS pricing pages (Mobbin Sites) | Shipped + LIVE-VERIFIED -- merged main PR #174 (4f28d97), on prod. Services pricing clarity: 'Most popular' badge + ring/scale emphasis on the Hybrid card (slug-matched via service.slug=='hybrid', not name), tightened per-card CTAs (Join the team / Start online / Start hybrid / Start in-person via CTA_BY_SLUG), and the team start-date announcement block surfaced on Services (mirrors Index; loadTeamPlanSettings switched to .maybeSingle()). ComparisonTable untouched. Verified live on theigu.com/services after a hard-reload past a stale apex cache: Hybrid badge + emphasis, 4 tightened CTAs, prices 10/30/95/145, announcement renders ('Next team program starts soon!'; next_program_start_date null so the date sub-line is not exercised). tsc+build clean per CC. Note: PUB2 also pre-existed inside the Capacitor Phase-1 commit; de-duped during the feat/capacitor-mobile detangle (now main-only).
PUB3 | Public / Marketing | Trust / credibility | Surface coach credentials/certs, any guarantee, and Kuwait-localized trust signals | Trust is the conversion lever for paid coaching | P1 | M | MeetOurTeam.tsx, CoachProfile.tsx | Future / Centr coach bios | Shipped + LIVE-VERIFIED (2026-06-23) -- merged main PR #176 (450a458), live on prod. MeetOurTeam coach cards now surface a 'Certifications' block (Award icon + first 2 qualifications as outline badges + '+N more') ABOVE Specializations, gated on coach.qualifications. Verified live on theigu.com/meet-our-team (authenticated client session): lead coach (Hasan Dashti, Lead badge + red ring) shows Certifications = 'MB BCh BAO (Hons)' / 'ACE-CPT' / '+7 more', then Specializations (General Fitness/Strength Training/Bodybuilding/+6 more). Lead styling / CoachDetailDialog / specializations untouched; free-text quals rendered directly (no getLabel). tsc+build clean; diff matches spec. CONTENT (Hasan): lead coach short_bio (the philosophy/standout line) is still empty -- card shows no standout line; populate a 1-2 sentence standout per coach.
PUB4 | Public / Marketing | Mobile landing | Mobile-first hero + sticky primary CTA; fast LCP (hero already preloaded) | Mobile-heavy audience; conversion | P1 | S | Index.tsx, hooks/use-mobile | Mobile landing best practice | Shipped (code) — merged main PR #170 (4414be8), live on prod. Mobile sticky CTA bar (single-source primaryCta + IntersectionObserver, md:hidden, safe-area pb) + hero LCP <link rel=preload as=image>. tsc + build clean, faithful diff. LIVE MOBILE SMOKE NOT YET DONE: landing '/' is unreachable in waitlist mode (anon -> /waitlist, logged-in -> /dashboard) + Chrome resize didn't give a true <=767px viewport. Self-verifies at launch (waitlist off); or add a mocked-logged_out component test for durable coverage.
PUB5 | Public / Marketing | How It Works | 3-4 outcome-focused steps with icons | Clarifies the offer quickly | P2 | S | marketing/HowItWorksSection.tsx | Standard pattern (flat bar) | UPGRADE 2026-07-12 -- re-spec HowItWorksSection to flat surfaces, mono step labels, crimson accents. See recon 2026-07-12.md SPEC: DESIGN_UPGRADE_SPECS_BATCH2_2026-07-12.md.
PUB6 | Public / Marketing | Testimonials | Lead with outcomes/results, not just star ratings; author + result | Stronger social proof | P2 | S | Index.tsx testimonials, Testimonial.tsx | Contractbook outcome-led testimonial grid (mobbin.com/sites/sections/e66be7ae-4850-4bf8-8327-64e641e1c6b3) + Shade case-study cards (…/ba35c5dc) | UPGRADE + BIGGER BUG (CC 2026-07-12): (1) reorder card lead-with-outcome (order today stars:109-119>quote>proof:121-123>author). (2) FABRICATED social proof -- TestimonialsList.tsx:142-162 renders 3 fake 5-star "Client Name/Program Type" cards when no featured testimonials (also the error fallback :87). PUB6 asked AUTHENTIC -> killing the fakes is the bigger win. (3) no useTranslation on i18n public page. Spec: DESIGN_UPGRADE_PASS_2026-07-12.md
PUB7 | Public / Marketing | FAQ | Ensure the FAQ answers real objections (price, commitment, refunds, medical) | Removes signup blockers | P2 | S | marketing/FAQSection.tsx | Standard pattern | KEEP + light UPGRADE 2026-07-12 -- content audit (price/commitment/refunds/medical) + flat accordion in current bar. See recon 2026-07-12.md
PUB8 | Public / Marketing | Brand cohesion | Align marketing visual language with the app (typography / colour / spacing) | One coherent brand from ad to app | P2 | M | layouts/PublicLayout.tsx, Footer.tsx, index.css | Internal consistency | SHIPPED + LIVE-VERIFIED 2026-07-04 (Cowork prod verify) -- strict app-parity flatten of public pages (removed gradients/raw rgba, tokenized) + BTN1 gradient-button retirement shipped alongside. Specs docs/PUB8_PUBLIC_PAGES_ALIGNMENT_BUILD.md + docs/BTN1_RETIRE_GRADIENT_BUTTONS_BUILD.md.
PUB9 | Public / Marketing | SEO / share | Per-page meta + OG share images via SEOHead | Discoverability + shareability at launch | P2 | S | SEOHead.tsx | Standard pattern | Shipped + LIVE-VERIFIED — merged main PR #171 (5da0522), on prod. og:image/twitter:image now ABSOLUTE https://theigu.com/og-image.png (was relative -> broke scraper previews) + width/height/alt/locale; Organization enriched (square logo, areaServed Kuwait, contactPoint) + ProfessionalService Kuwait node (no prices, pending level-pricing). Verified live via served-HTML head fetch; both JSON-LD blocks schema-valid (0 err). OG image already on-brand (IGU wordmark, 2400x1260). NOTE: CMS social_links all empty -> footer shows no socials + sameAs omitted (content to-do).
PUB10 | Public / Marketing | Waitlist | Clear value + a what-happens-next expectation on the Waitlist | Pre-launch capture quality | P2 | S | Waitlist.tsx | Standard pattern (flat bar) | UPGRADE 2026-07-12 -- re-spec Waitlist.tsx to current bar + explicit what-happens-next copy. See recon 2026-07-12.md SPEC: DESIGN_UPGRADE_SPECS_BATCH2_2026-07-12.md.
FU1 | Follow-up | statusUtils | Migrate getLoadColor / getLoadTextColor to the --status-* tokens | Full colour consistency with CC5 | P2 | S | lib/statusUtils.ts | — | KEEP 2026-07-12 -- token consistency (CC5). // Backlog
FU2 | Follow-up | Nutrition | Fold CoachNutritionProgress.signedExpectedChange onto classifyPhaseStatus | Stop client/coach phase-status logic diverging | P2 | S | nutrition/CoachNutritionProgress.tsx, lib/interpret.ts | — | KEEP 2026-07-12 -- dedupe phase-status logic. // Backlog
FU3 | Follow-up | Nutrition | Thread a real week-over-week % into TeamWeightProgressGraph so it can show a DeltaChip | Currently omitted (no upstream signed WoW) | P2 | S | nutrition/TeamWeightProgressGraph.tsx | — | KEEP 2026-07-12 -- needs upstream signed WoW first. // Backlog
FU4 | Follow-up | Client dashboard | Fix WeeklyProgressCard "This Week" weight-trend number — replace raw recent-minus-oldest over 14 logs with the smoothed weekly-average trend (consistent with NU1) and exclude zero/invalid weigh-ins | Pre-existing: a single zero/outlier weigh-in skews the number (e.g. +17.5 kg); surfaced during CC1/CC2 live review | P1 | S | client/WeeklyProgressCard.tsx | — | P1/BUG (bumped 2026-07-12, Hasan): data-correctness bug -- WeeklyProgressCard "This Week" trend skewed by outlier/zero weigh-in (e.g. +17.5kg). Fix = smoothed weekly-avg trend (NU1-consistent) + exclude zero/invalid. client/WeeklyProgressCard.tsx.
BUG1 | Bug fix | Planning board — exercise picker | ExercisePickerDialog desktop: make DialogContent a bounded flex-col (flex flex-col overflow-hidden) and the results list flex-1 min-h-0 (was fixed h-[400px] inside the default grid dialog). Covers Add Exercise + Add Replacements (same component). Optionally harden SwapExerciseDialog the same way. | On laptop heights the popup overflows max-h-[80vh]; list bottom + "Add N replacements" footer go out of bounds and cannot be reached | P1 | S | coach/programs/ExercisePickerDialog.tsx | — | Shipped — fix/planning-board-popup-scroll @ 2067c3d — verified live at 1280x720
BUG2 | Bug fix | Planning board — progression rules | ProgressionRulesSheet desktop: swap Radix ScrollArea -> DrawerScrollArea (app-standard native scroller). Radix viewport did not engage scroll in the flex-1 min-h-0 column; v2 taller content exposed it on desktop (was mobile-only). | Progression rules list cannot scroll on desktop | P1 | S | coach/programs/muscle-builder/ProgressionRulesSheet.tsx | — | Shipped — fix/planning-board-popup-scroll @ 2067c3d — harness-verified (scrollHeight 918 vs clientHeight 336, scrollTop 0->400)
WK7 | Workout | Logging (redesign) | Redesign the logging UI: session OVERVIEW on Start (today's exercises + progress ring + Begin/Resume) -> one-exercise-at-a-time FOCUS mode (active set dominant; completed sets collapse to a one-line summary; prescription as one compact line not a chip stack; last-time/PR inline; rest timer inline) -> COMPLETION SUMMARY (volume / PRs / time). Keep the input mechanics (already good); presentation only. | Current screen is a 29-set single scroll of dense chip-stacks (Hasan: 'very primitive, too much text'). Focus + visual hierarchy is the biggest premium lift on the highest-traffic client surface. | P1 | L | WorkoutSessionV2.tsx (reuse setLogs/completeSet/RestTimer). Pairs with WK2 timer fix + BUG6 mobile picker. Do NOT touch completeSet save path (see BUG3). | Strong (per-exercise focus); Hevy (active-set + session summary); Fitbod (big inputs) | Shipped + deployed — WK7 logging rewrite (Phase1 e9f9f6b + Phase2 f558e85 + batched-loader source-fix 2089354, deploy 6b1eaf6). Live on prod. Also fixed BUG3 root cause (loadSession query batching).
NU7 | Nutrition | Goal setting | Visual-first goal page: calorie HERO + macro DONUT/ribbon (reuse NutritionPhaseCard) replacing the 11 label:value rows; body-fat JOURNEY arc (start->current->target) + phase timeline; goal-type/rate as a formatted header chip; 'All numbers' disclosure keeps the raw figures. Polish: don't render kcal in destructive red; format 'Fat_loss'->'Fat loss'. | Hasan: same numbers could be shown with rings/graphs to feel premium. Extends the CC1/CC2 visual language onto the still-plain goal page. | P2 | M | nutrition/NutritionGoal.tsx (current body-fat from NutritionProgress source); values via calculateNutritionGoals() - no inline BMR/TDEE math. Coupled to BUG5 load error. | MacroFactor/Carbon (calorie hero + donut); Lifesum (macro rings); Zero (body-comp arc) | Shipped + deployed — feat/nu7-goal-visuals merged main (4aa82a9), live on prod 2026-06-19 (calorie hero + macro donut + body-comp journey arc + macro --tokens).
CAL1 | Coach | Program calendar (mobile) | Mobile redesign of the program-publishing calendar: branch on useIsMobile() -> swipeable WEEK STRIP + vertical full-width DAY LIST (day/date, session title, Draft/Published/Rest status chip, tap-to-edit, inline per-day publish) instead of 7 squeezed columns. Reuse muscle-builder MobileWeekStrip/MobileDayDetail. Desktop unchanged. New sheets use vaul Drawer + DrawerScrollArea (not Radix ScrollArea - see BUG8). | Hasan: 'the calendar view for publishing workouts on mobile is not nice at all and needs a redesign.' 7 columns on a phone = tiny cards + wasted vertical space. | P2 | M | coach/programs/ProgramCalendarBuilder.tsx; reuse muscle-builder/Mobile* components | Own muscle-builder mobile pattern; coach/planner refs in IGU-Mobbin-Reference-Library.md | Shipped + deployed — feat/cal1-mobile-calendar FF-merged main (d428bf2), live on prod 2026-06-20. useIsMobile day-list + status chips + per-session inline publish + swipe Copy/Delete + per-day bulk publish + swipeable week strip; desktop 7-col grid byte-identical; weekday-label bug (global vs within-week dayIndex) fixed via % 7.
BUG3 | Bug fix | Workout logging (load) | Client couldn't log / 'Set didn't save' / workout won't complete. CORRECTED root cause (RLS theory disproven live): WorkoutSessionV2.loadSession fires ~N×3 concurrent per-exercise reads (~20 for a 7-exercise day); client_module_exercises + embedded exercise_library read intermittently 500s under the cold/concurrent burst (transient pooler error) -> client stranded on loading skeleton. Fix shipped: selectWithRetry() + error state (band-aid). SOURCE FIX in WK7 §1.5: batch per-exercise history/PB into 2 reads keyed by exercise_ids. | Launch-blocker - core client feature broken; sets silently lost. | P0 | M | WorkoutSessionV2.tsx loadSession (selectWithRetry shipped); WK7 §1.5 batches the reads | - | Shipped + deployed — SOURCE FIX landed: selectWithRetry + batched per-exercise reads (.in(exercise_ids) / .in(instance_ids)) in WorkoutSessionV2.loadSession (commit 2089354, WK7 §1.5). Mitigation + source fix both on main. P0 CLOSED. Verified at HEAD d428bf2.
BUG4 | Bug fix | Client dashboard | Today's Workout card: 'Start Workout' button too wide -> 'Calendar' button pushed out of bounds on mobile. Make the button row shrink/wrap so both fit. | Calendar action unreachable on phone. | P1 | S | Today's Workout card (client dashboard) | - | Shipped — TodaysWorkoutHero button row is now flex gap-3 + flex-1 min-w-0 (icons shrink-0) so Start/Continue + Calendar both fit on mobile; landed in bug-bucket layout PR #162 (72de29d). Verified at HEAD d428bf2.
BUG5 | Bug fix | Nutrition goal | 'Failed to load nutrition goal' intermittent load error on the goal page - investigate the fetch (RLS / flaky RPC). | Goal page intermittently errors; coupled to NU7 redesign (land bug first). | P1 | S | nutrition/NutritionGoal.tsx fetch | - | Shipped — NutritionGoal.loadActiveGoal now .order(created_at desc).limit(1).maybeSingle(); guards the duplicate is_active row that made maybeSingle throw (the intermittent 'Failed to load nutrition goal'). Verified at HEAD d428bf2.
BUG6 | Bug fix | Workout logging (mobile) | Mobile replacement-exercise picker: the whole sheet drifts up/down and the title clips off-screen (distinct from the shipped desktop ScrollArea fix; likely vaul Drawer + keyboard). Bound the mobile sheet + pin the title. | Replacement flow unusable on mobile; coupled to WK7 logging redesign. | P1 | M | replacement-exercise picker (mobile / vaul Drawer) | - | Fixed (code-verified) -- merged main PR #177 (16bdf99), auto-deploys to prod via Vercel. Root cause: vaul ^0.9.9 defaults repositionInputs=true, so focusing the search field lifted the bottom sheet (the drift) and the keyboard-unaware max-h-[92dvh] pushed the 'Swap Exercise' title off-screen (the clip); the prior autoFocus-off only delayed it to the manual tap. Fix: SwapExercisePicker mobile Drawer (WorkoutSessionV2.tsx ~L1196) now passes repositionInputs={false} + shouldScaleBackground={false} -- the proven MobileDayDetail pattern -- so vaul stops translating the sheet and the title stays pinned above the keyboard. Coach SwapExerciseDialog (no input) + desktop overlay untouched; autoFocus kept off on mobile. tsc+build clean; diff matches spec. ON-DEVICE ACCEPTANCE TEST PENDING (NOT reproducible in desktop Chrome): iOS Safari + Android Chrome / Capacitor -- start session -> Swap -> tap Search -> sheet stays put, title visible, filter+select work, desktop unchanged. Follow-up (separate, not BUG6): other input-bearing mobile Drawers (ExercisePickerDialog, CoachClientThread composer, MacrocycleEditor) may share the latent issue -- same one-line fix if reported.
BUG7 | Bug fix | Client dashboard | Client's 'Your Coach' shows 'HD-RPC-Test' instead of the real coach - verify get_coach_for_client resolution. Likely test-env data, confirm. | Wrong coach shown on client account (probably test data). | P2 | S | get_coach_for_client RPC; client 'Your Coach' card | - | Reported - bugs cowork (likely test data) // Reviewed 2026-07-12: likely test data, verify at build.
BUG8 | Bug fix | Cross-cutting dialogs | Radix ScrollArea inside max-h dialogs doesn't scroll (Viewport h-full can't resolve % height through an indefinite-height flex chain -> Viewport expands to content; maxScroll 0). FIX: added DialogScrollArea plain-overflow primitive (mirrors DrawerScrollArea); swapped ProgressionRulesSheet + 7 in-dialog sites + responsive-dialog desktop bounding/footer-pin + MesocyclePicker. | Coach couldn't scroll progression rules / long in-dialog lists; systemic across ~20 sites. | P1 | M | ui/dialog.tsx (DialogScrollArea); ProgressionRulesSheet; responsive-dialog; CoachManagement/AdminBillingManager/PricingAuditLogDialog/TeamMemberNutritionDialog/AddSpecialistDialog/SessionLogViewer; MesocyclePicker | - | Shipped + deployed - feat/dialog-scroll-area (merged main 2026-06-18)
WK8 | Workout | Logging (units) | kg/lb weight entry + live conversion. DB stays canonical kg ALWAYS (performed_load, prescriptions, charts, progression). Per-client display pref in client_preferences(user_id, weight_unit) self-RLS; kg¦lb segmented toggle in the session header live-converts inputs/history/PR + relabels; save via toCanonicalKg, load via fromCanonicalKg (src/utils/weightUnits.ts, never inline the factor). | Clients want lb entry; DB must stay kg so charts/progression/coach views are unaffected. | P1 | M | WorkoutSessionV2 UI (WK7 §4) + useWeightUnit hook + weightUnits.ts; backend done commit bd2e5db | - | Shipped + deployed — built in WK7 rewrite (kg/lb via weightUnits.ts, client_preferences). Live on prod.
WK9 | Workout | Logging (skip) | Skip recorded for coach, 3 levels: day = skip_client_day_module(p_module_id) (status 'skipped'+skipped_at); exercise = skip_client_exercise(p_cme_id,p_skipped) (client_module_exercises.skipped); single set = exercise_set_logs row skipped=true + null performed_* (no RPC). Skipped counts as addressed for completion but renders distinct (neutral token) from completed/missed. | Clients need to skip work; coach adherence must distinguish skipped from missed/incomplete. | P1 | M | WorkoutSessionV2 UI (WK7 §5); RPCs + skipped cols backend done commit bd2e5db | - | Shipped + deployed — built in WK7 rewrite (skip RPCs/cols: skip_client_day_module / skip_client_exercise). Live on prod.
BUG9 | Bug fix | Coach dashboard home (mobile) | /coach dashboard index error-boundaried ("Something went wrong") at mobile width on the phone during CAL1 review. | Looked like a real data/mobile crash; blocked the CAL1 live review and triggered a long investigation. | - | - | CoachDashboardOverview + index widgets (none changed) | - | Resolved — NOT a real bug. Stale cached dev bundle on the phone (long session: many HMR reloads + 2 LAN-IP changes + mirror reconnects) -> module load failure -> error boundary (same family as the SPA stale-chunk pattern). Disproven: CC faithful DB rebuild of the payment-exempt-sub shape + activity data rendered CLEAN in both Playwright Chromium AND real WebKit; and prod theigu.com/coach renders perfectly with the same real coach data. Dev-session artifact, not prod.
WA1 | Messaging | Workout completion | Add a "Message coach about this session" WhatsApp deep-link on the 1:1 workout completion sheet, pre-filled with the WK7 session recap (volume/sets/time/new PRs). | Flagship of the hybrid messaging direction; WhatsApp is the preferred client<->coach channel in-region; reuses existing WK7 summary + coach whatsapp_number. | P1 | S | WorkoutCompletionSheet.tsx, WorkoutSessionV2.tsx, + get_coach_whatsapp_for_client RPC migration | Ladder/Future coach contact | Shipped (code + RPC verified) — merged main PR #173 (b188445), live on prod. get_coach_whatsapp_for_client RPC registered (20260621120000 via migration repair+db push), SECURITY DEFINER, EXECUTE to authenticated/service_role only (anon denied). 'Message coach about this session' button on 1:1 workout-completion sheet (mobile+desktop), wa.me deep-link pre-filled from WK7 summary; team_plan excluded; separate ref-guarded fetch (not in loadSession burst). tsc+build clean. LIVE VISUAL smoke pending a 1:1 client + coach whatsapp_number set (team session won't show it by design). Bonus: 7 drifted WK8/WK9 migrations (20260619*) reconciled into schema_migrations.
NU8 | Client | Nutrition (Team + 1:1) | Consolidate the client nutrition pages into one scroll: remove the Goal Setting/Progress Tracker top tabs AND the nested Progress/Graphs tabs; targets hero with an Edit-targets sheet, inline trend (range + Weight/Body-fat toggle), weekly check-ins. Unify team + 1:1. | Removes 3-layer redundant tab nesting; information scent; Mobbin-grounded. | P1 | L | TeamNutrition.tsx, NutritionProgress.tsx, NutritionGoal.tsx, ClientNutrition.tsx | MacroFactor / Lifesum / Yazio / Alma / MyFitnessPal (ios) | BOTH PHASES SHIPPED + LIVE-VERIFIED (2026-06-23). Client nutrition consolidated to one scroll, zero tabs, team + 1:1 sharing the shape (hero -> log -> trend -> weekly input). PHASE 1 (team, PR #179 7f8e92b): /nutrition-team verified live via a team client -- no tabs, hero + macro ribbon + 'Edit targets' Dialog hosting the goal editor in-context, 4W/12W/All range + Weight¦Body-fat toggle, WeekCard check-ins. PHASE 2 (1:1, PR #180 69c9729): /nutrition-client verified live via a seeded 1:1-Online test client -- NutritionPhaseCard hero (read-only, 'On Track', 2100 kcal + ribbon, expected vs actual rate strip computed from seeded weight logs) + 'Message coach to adjust' link + weekly ribbon + inline Log Today + trend (range/toggle on real seeded data, weight line vs target) + 'This week' ClientNutritionProgress form. No tabs. NutritionGoal gained optional onSaved. tsc+build+eslint clean on both. TEST ACCOUNTS (payment-exempt, +alias emails): Team / 1:1 Online / 1:1 Hybrid / 1:1 In-Person created by Hasan; 3 1:1 accounts seeded with active nutrition_phases (Summer Cut / Lean Bulk / Fat Loss Phase) + 9 weight_logs on Online -- retained for ongoing feature testing. REMAINING: mobile Drawer + keyboard (NU Phase 1 Edit-targets sheet, repositionInputs=false) still needs a phone/Capacitor pass. FOLLOW-UPS (minor): stray ?tab= links in QuickActionsGrid/AlertsCard now no-op; loadData 'No Active Goal' destructive toast on first-time no-goal path -- soften.
SE1 | Sessions | Coach SessionsTab + client /sessions | Redesign to grouped Upcoming/Past lists (date chips + status pills) both sides; then request->confirm booking (client requests status=requested -> coach confirms/declines); availability slots later phase | Sessions surface is a bare ad-hoc digest; both coach+client need to book; clean Sessions(appointments) vs Workouts(training) boundary | P1 | L | client-overview/tabs/SessionsTab.tsx, pages/sessions, direct_calendar_sessions | Zomato Your Bookings Upcoming/History+status pills (mobbin.com/screens/b2da1a7b-4031-4299-88e6-4942956cd1bc); Urban Company (…/d2b44cff); Redfin (…/3e51ab5e) | RE-SPEC FROM SCRATCH (CC 2026-07-12): spec targets the WRONG system. Client /sessions (ClientSessions.tsx:135,147,168) reads session_bookings+coach_time_slots+book_session_atomic, NOT direct_calendar_sessions (only 2 coach components read that). "both surfaces read d_c_s" false; "extend status CHECK" moot (no CHECK, free text 20260205:76); availability model ALREADY ships (coach_time_slots/CoachSessions.tsx). ARCH DECISION: build request->confirm on existing session_bookings [rec] vs unify d_c_s. Gates AD4+GC1+BUG13; orphans /coach/sessions. DECISION LOCKED 2026-07-12: build request->confirm on EXISTING session_bookings/coach_time_slots (not a parallel d_c_s system). Re-spec pending. SPEC: DESIGN_UPGRADE_SPECS_BATCH2_2026-07-12.md.
WK10 | Workout | Coach client Workouts tab | Calendar-forward week grid + per-day +menu (Blank / Saved / Assign program in-context / Create program scoped to client) + Program history strip; reuse DirectClientCalendar/AssignFromLibraryDialog/ClientProgramList | Today Assign navigates away + calendar hidden in a Sheet; no at-a-glance week; building custom program abandons the client page | P1 | L | client-overview/tabs/WorkoutsTab.tsx, coach/programs/* | Runna Training calendar per-day +Add (mobbin.com/screens/86245523-ea19-44cd-bb20-5b52f0bbaa88); Aaptiv Edit My Plan (…/d0021aaa) | KEEP 2026-07-12 (upgrade spec) -- ground authoring +menu in TrueCoach/Runna at build. // PARTIAL (verified 2026-07-05 recon): B5 read-only week/month coach calendar (ClientScheduleCalendar) exists; the WK10 net-new piece = per-day +menu authoring (Blank/Saved/Assign program/Create) is OPEN. SPEC: DESIGN_UPGRADE_SPECS_BATCH2_2026-07-12.md.
GC1 | Sessions | Coach + client | Google Calendar 2-way sync of booked sessions (OAuth + Calendar API + token storage/refresh; reminders; later read busy-times). Must work inside Capacitor WebView for native. | Sessions land in the personal calendars both sides actually live in; reduces no-shows | P2 | XL | new edge fns + token table; direct_calendar_sessions | Calendly GCal connect | KEEP 2026-07-12 (future) -- gated on Sessions booking Phase 2. Correctly parked. // Future phase - after Sessions booking (Phase 2) ships. Captured; not started
PR1 | Progress | Coach client Progress tab | Add CC1 metric-card summary row (weight/body-fat/volume + deltas + sparklines) + status header above the existing weight-trend hero; two-up Measurements + Volume below. Display-only regroup of CoachNutritionGraphs + VolumeChart | Raw chart dump today; the numbers a coach scans first arent surfaced; no shared visual language | P2 | M | client-overview/tabs/ProgressTab.tsx, CoachNutritionGraphs, VolumeChart | Oura/WHOOP insights; CC1 metric card | CLOSED 2026-06-26 — SUPERSEDED by CO12: the Progress tab was removed entirely (its CoachNutritionGraphs already lived in Nutrition->History; VolumeChart in Workouts) and a compact weight trend was promoted onto Nutrition->Overview. Redesign moot.
CARE1 | Care Team | CareTeamCard + CareTeamMessagesPanel | Polish roster to role-coloured chips (coach/dietitian/physio) + staff-only banner; restyle team thread to own-vs-other bubbles w/ mentions. Presentation pass, no schema/RLS change | Components predate the current card/chip/thread language; read as a flat list + log | P2 | M | coach/CareTeamCard.tsx, nutrition/CareTeamMessagesPanel.tsx | Slack threads; clinical care-team UIs | DONE (verified 2026-07-12): role chips CareTeamCard.tsx:85-95,321 + staff-only banner :236-240 + own/other bubbles CareTeamMessagesPanel.tsx:403-467 all confirmed; only optional @-mentions absent -> close (split a new low-pri row if wanted). // LARGELY SHIPPED (via specialist-parity S1-S5 + messaging work) -- verified 2026-07-05. CareTeamCard has header + Add Specialist (gated) + staff-only banner (Lock, line 237) + role-coloured chips (SPECIALTY_CONFIG) + Ends chip + You badge + kebab discharge/terminate. CareTeamMessagesPanel has threaded own/other bubbles (isOwn->flex-row-reverse + bg-primary vs bg-muted, line 404-438) + avatars + pinned composer. Spec substance done. REMAINING = cosmetic only (raw Tailwind chip colors bg-green-100 vs redesign token soft-pills; specialty ICON avatars vs initials; own-bubble bg-primary vs --color-background-info; @mention highlight unconfirmed) -- optional P2 polish, not a required slice.
PF1 | Profile | Coach client Profile tab | Add identity header card (avatar+name+plan+status pill); swap shadcn Badges for the standard rounded status pills; auto-fit the demographics grid. Light polish, already well-built, read-only kept | Tab leads straight into a stat grid with no face; badge style inconsistent with the rest of the redesign | P3 | S | client-overview/tabs/ProfileInfoTab.tsx | CRM contact records | SHIPPED + COWORK-VERIFIED ON PROD 2026-07-05 (commit 29e4a06, bundle index-DHCwaafi). ProfileInfoTab now leads with an identity header card (avatar initials + name + <plan> subtitle + soft status pill; client-since from submission.createdAt, omitted when null); subscription + onboarding shadcn Badges swapped to the redesign soft-tinted rounded-full pill (border-status-X/40 bg-status-X/10 text-status-X via a shared inline StatusPill, colors via getSubscriptionStatusVariant); demographics/onboarding grids -> auto-fit minmax(8rem,1fr) reflow (CC deviated from spec minmax(0,1fr) which would 1-up-collapse). Verified live coach viewing +online: header + soft Active pill render, pills consistent w/ Overview/Nutrition, no console errors (stale HX1-bundle auth transients only). NOT exercised (data, not bugs): client-since populated + review-needed medical rail (no test client w/ a submission handy). NOTE: deploy served the prior bundle (5d0cjs_P) on first check, propagated to DHCwaafi on retry -- CDN timing, hard-reload before trusting.
CL11 | Client | Client dashboard (NewClientOverview) | Visual polish to coach-grade language: drop gradient bg for flat surface; add CC1 glance-card row; emerald rail on Todays Workout hero; MacroDistributionRibbon on nutrition target card; rounded status pills; demoted Account group. IA from CL1 unchanged | Dashboard still uses gradient bg + generic border cards; reads as a different product from coach surfaces + the shipped Nutrition tab | P2 | M | client/ClientDashboardLayout.tsx, client/NewClientOverview.tsx + composed cards | Coach Overview/Nutrition (own); Runna/Caliber home | Increment 1 SHIPPED (commit a9b7fa6): flat surfaces (drop gradients) + macro ribbon on daily targets. Remaining: optional glance row + status-pill pass. Spec docs/CL2-Client-Dashboard-Polish-Spec.md [ID renamed CL3->CL11 2026-06-26 to resolve collision with CL3 LogTodayCard row 12.]
NU9 | Client | Client nutrition This-week form (ClientNutritionProgress) | Restructure the weekly tracking form into a completion-state card stack (weigh-ins/steps/bodyfat+circumference/weekly check-in) w/ status rails + chips matching ClientWeeklyRibbon; mobile Drawer for the heavy inputs. Keep all writes incl bodyfat dual-write | Only laggard on /nutrition-client: still generic shadcn cards, no completion signalling; heaviest client interaction | P2 | M | nutrition/ClientNutritionProgress.tsx | Coach Nutrition (own); habit trackers | Increment 1 SHIPPED + LIVE-VERIFIED 2026-06-25 (974b17d): This-week completion anchor (rail + chips) + removed dead Add Inputs button. Optional follow-up: section-card rails. NOTE pre-existing phase-week vs calendar-week count mismatch (anchor 0/3 vs ribbon 1/3)
CO9 | Coach | My Clients master-detail grid | Collapse the master COLUMN width (340px to 220px) when a client is open, not just the card content -- the point of collapsing is to hand the freed width to the detail pane. Smooth grid-template-columns transition | Polish batch condensed the card content but kept the 340px column, so the detail pane gained no room (Hasan caught live) | P2 | S | coach/CoachClientsWorkspace.tsx:351 | TrueCoach/Linear master-detail | Shipped (commit ad62f40); pending Vercel deploy + post-deploy smoke
BUG10 | Bug fix | Coach client detail: Progress/Overview/Nutrition | Coach saw "No measurements available" despite client weigh-ins existing. Root cause: weight_logs/circumference_logs coach SELECT keyed on nutrition_phases.coach_id (NULL on seeded phase + stale after reassignment). Fix: relationship-based policy via is_care_team_member_for_client, mirroring body_fat_logs | Coach progress surfaces were empty even with logged data -- silently useless for any client whose phase.coach_id is NULL/stale | P1 | S | migration 20260624140000; weight_logs + circumference_logs RLS | n/a | SHIPPED + LIVE-VERIFIED 2026-06-24 (applied out-of-band; coach now sees 9 weigh-ins, -1.0kg, chart). Migration file pending commit + db push register
BUG11 | Bug fix | Client nutrition (/nutrition-client) | Weigh-in count disagreed on the same page: top ribbon showed 1/3 (IGU calendar week) while the new This-week anchor + check-in save-gate showed 0/3 (phase-week). Aligned ClientNutritionProgress anchor + save-gate + N-more notice to startOfIguWeek, matching ribbon + dashboard | User sees two different weigh-in counts seconds apart; save button gated on a different number than displayed | P2 | S | nutrition/ClientNutritionProgress.tsx | n/a | SHIPPED + LIVE-VERIFIED 2026-06-25 (459befe): anchor now reads 1/3 in agreement with the ribbon
CL6 | Client | Client dashboard (NewClientOverview) | Recompose dashboard into MAIN + RAIL: full-width Today hero on top; main column = nutrition target / this-week / adherence; rail = log today / coach (WhatsApp) / care team. Columns flow independently so short rail cards fill height vs a taller main -- no dead space. Replaces the forced equal-2col pairs | Cards stacked full-width even when small (e.g. Log Today = 2 inputs) -- wasted space, poor scan on desktop | P2 | S | client/NewClientOverview.tsx | n/a | SHIPPED + LIVE-VERIFIED 2026-06-25 desktop+mobile (609a9e9; earlier 2col fc77900). Balanced, important-first, grouped per Hasan geometry/flow note
CL7 | Client | Standalone client pages (nutrition, calendar, team-nutrition) | New ClientPageLayout shell (SidebarProvider + ClientSidebar + flat bg). Wrapped ClientNutrition + TeamNutrition so the left nav persists + gradient dropped. WorkoutCalendar gets it via WK10 | Sub-pages rendered bare -- left sidebar disappeared + still had the old gradient bg (inconsistent w/ flat dashboard). Hasan flagged it repeated across sub-pages | P1 | M | components/layouts/ClientPageLayout.tsx (new); pages/ClientNutrition.tsx; pages/TeamNutrition.tsx | n/a | SHIPPED + LIVE-VERIFIED 2026-06-25 (9937518 + bd66f70): ClientPageLayout shell wraps ClientNutrition, TeamNutrition, WorkoutCalendar, Messages, ExerciseHistory, AddonsCatalog. REMAINING: ClientSessions (4 returns) + shared multi-role Account/WorkoutLibrary/EducationalVideos (need role-aware layout) [UPDATE 2026-06-25: REMAINING done by CL10 -- ClientPageLayout now role-aware + wraps ClientSessions/Account/Learn.]
CL8 | Client | Dashboard Your Coach card (CoachCard) | Surface the WhatsApp contact-coach button on the dashboard (was only wired into the post-workout completion sheet). Green Message on WhatsApp button w/ the real WhatsApp glyph, gated on coach having a number, via get_coach_whatsapp_for_client RPC; stopPropagation so it does not trigger the cards profile-nav | Built WhatsApp contact feature was invisible to clients on the dashboard; Hasan asked where it was + wanted the real WA logo | P2 | S | client/CoachCard.tsx | n/a | SHIPPED + LIVE-VERIFIED 2026-06-25 (550c964): green WhatsApp button renders on Your Coach card
CL9 | Client | Client nutrition page (/nutrition-client) | Regroup desktop layout: Row A = target/calorie phase card beside the trend graph; Row B = weekly ribbon + daily log paired; This-week form full width. lg breakpoint (sidebar eats width on md) | Cards stacked full-width single column -- oversized for content, related info (target + graph) not grouped. Hasan flagged grouping + sizing | P2 | M | pages/ClientNutrition.tsx | n/a | SHIPPED + LIVE-VERIFIED 2026-06-25 (3fcf6dd): phase card beside graph, not cramped; ribbon+log paired
WK11 | Workout | Client workout calendar (/client/workout/calendar) | Rebuilt the bare month-grid-with-dots into a WK10 week-grid: 7 day columns w/ color-coded session chips (title + completed/scheduled), week nav + This-week jump, today highlighted, in the ClientPageLayout shell. Mobile = Runna-style day list. useClientWorkoutsWeek extended w/ title+date | Calendar opened standalone (no left nav) + looked nothing like the WK10 design we built (was month dots). Hasan flagged both | P1 | L | pages/client/WorkoutCalendar.tsx (rewrite); hooks/useClientWorkouts.ts | TrueCoach week calendar; Runna day list | SHIPPED + LIVE-VERIFIED 2026-06-25 (7608f0c) desktop + mobile; seeded a test program to confirm chips render
NU10 | Nutrition | Weekly check-in (ClientNutritionProgress) | Unify the whole weekly check-in into ONE guided surface: 3-level adherence scale (on_point/mostly/off_track + weighed/estimated/guessed) replacing yes/no; grouped Adherence + How-you-feel (changes + note) + cadence-gated Measurements (weight always; circumference odd weeks; body fat every 4th) with Steps folded in; dimmed dietitian-scoped Advanced seam. Persists note + physical_changes on adherence_logs. | Scattered adherence+changes across cards; richer signal; one phase-scoped write; extensible to dietitian questions. | P1 | M | nutrition/ClientNutritionProgress.tsx; nutrition/NutritionProgress.tsx; supabase/migrations 20260625120000 + 20260625130000; integrations/supabase/types.ts | visualize mock client_unified_checkin | SHIPPED + LIVE-VERIFIED 2026-06-25 (a55d9b6 + 5f681a0 + 8144fb0): 3-level scale + derived compat booleans (lenient: mostly/estimated=true) so coach roster % math unchanged; steps fold-in; notes+physical_changes on adherence_logs. Caught + fixed pre-existing weekly_progress.goal_id FK landmine (nutrition_phases vs nutrition_goals disjoint) that 409d notes/body-fat for ALL phase clients -- check-in no longer writes weekly_progress; body fat relies on body_fat_logs. Supersedes NU9.
CT5 | Content | Library (Learn) | Merge Exercise Library + Educational Videos + Learning Paths into one /learn area: segmented Exercises . Videos . Pathways over a shared search; Exercises keeps full taxonomy facets; admin keeps video CMS in Videos tab; coach gets preview + assign. Old routes redirect; all nav repointed. | Three fragmented content surfaces; stop spreading features -- unify+simplify (Mobbin: NTC/MasterClass/Headspace single library + segmented tabs). | P2 | L | pages/Learn.tsx (new); components/learn/ExercisesTab.tsx + VideosTab.tsx (new); lib/routeConfig.ts; client/ClientSidebar.tsx; Navigation.tsx; client/QuickActionsGrid.tsx; App.tsx | Nike Training Club / MasterClass / Headspace | SHIPPED + LIVE-VERIFIED 2026-06-25 (57321da) desktop+mobile: segmented Exercises/Videos/Pathways + shared search + full taxonomy facets; /workout-library and /educational-videos redirect into /learn; mobile dock shows Learn. Admin video-CMS + coach assign branches preserved.
WK12 | Workout | Workouts area (/client/workout/calendar) | Rename calendar -> Workouts; Schedule/History in-page tabs (fold Exercise History in, remove its separate nav item); Week/Month toggle (default Month); month grid w/ status dots + legend + This-week enriched brief list (exercise count + primary muscles + Done/Due/Scheduled/Missed rails); enriched week chips; Message-coach button (-> /messages); tap a month day to jump to that week. | Calendar was a bare week-grid; enrich + unify; month view is denser (Hasan pref); brief = exercise count + primary muscles. | P2 | L | pages/client/WorkoutCalendar.tsx (rewrite); components/workouts/ExerciseHistoryPanel.tsx (new); hooks/useClientWorkouts.ts (enriched month/week selects + deriveModuleBrief); lib/routeConfig.ts; client/ClientSidebar.tsx; Navigation.tsx; App.tsx | Runna / Nike Training Club | SHIPPED + LIVE-VERIFIED 2026-06-25 (57321da) desktop+mobile: Schedule/History tabs, Month default w/ status dots+legend + This-week briefs (status rails/pills), Week toggle enriched chips (count + status), folded ExerciseHistory panel, Message-coach, /client/workout/history redirect, dock renamed Workouts. (Seeded test program has 0 module_exercises so briefs show 0 exercises/no muscles -- count logic correct; real programs populate muscles.)
CL10 | Client | Role-aware ClientPageLayout + audit tail | Make ClientPageLayout ROLE-AWARE (client -> full sidebar shell; coach/admin -> bare, top-nav only w/ correct role) via warm useRoleCache + fallback user_roles fetch. Wrap Learn, AccountManagement (2 branches), ClientSessions (4 branches) so staff stop getting the client sidebar / forced client role on shared multi-role routes. | Completes CL7: shared multi-role pages either lost the nav (bare) or would force the client shell on coaches/admins. | P1 | M | components/layouts/ClientPageLayout.tsx; pages/Learn.tsx; pages/AccountManagement.tsx; pages/ClientSessions.tsx | - | SHIPPED + LIVE-VERIFIED (client side) 2026-06-25 (57321da): client gets the sidebar shell on Learn/Workouts/Account; Account shows only the Account tab (no Coach Profile) for a client. PENDING: coach-login pass to confirm staff get the BARE shell (no client sidebar) on a shared route.
CT6 | Coach | Coach Hub (/coach/hub) | New coach-only education area: segmented Training / Library / Resources over shared search. Library = advanced coach-only videos (category+level filters); Resources = ebooks/links + courses/certifications (redirect out). Generalized coach_educational_content (content_type/section/category/level/external_url/author); admin CMS extended; training gate scoped to section=training. | Centralizes advanced coaching education separate from client content; closes an RLS leak where any authenticated user could read coach content. | P2 | L | src/pages/coach/CoachHub.tsx; CoachTrainingDashboard.tsx; admin/CoachEducationalContentManager.tsx; routeConfig.ts; App.tsx; migration 20260625140000 | MasterClass; Crypto.com University | SHIPPED 2026-06-25 (c7dc303); coach live-verify pending
CO10 | Coach | My Clients workspace (desktop) | Collapse the master client list to a 48px rail when a client is open so the detail pane gets the full canvas; chevron+clients-icon+attention-dot to expand into the full picker; auto-collapse on select. Desktop only; mobile keeps the drawer. | Coaches need room to read an individual client’s cards on desktop; the 220px master ate width with no payoff once focused. | P2 | M | src/components/coach/CoachClientsWorkspace.tsx | Linear; Height (master-detail collapse) | SHIPPED 2026-06-25 (2863664); coach live-verify pending
CO11 | Coach | Coach shell + cards (design-language polish) | Flatten 3 leftover to-primary/5 gradients to bg-background (CoachDashboardLayout, CoachContentAssignments, TeamMemberNutritionDialog); swap macrocycle block <Card onClick> to ClickableCard (keyboard + aria-label). | Brings coach surfaces in line with the flat-dark design language and a11y card pattern used everywhere else. | P2 | S | src/components/coach/CoachDashboardLayout.tsx; CoachContentAssignments.tsx; TeamMemberNutritionDialog.tsx; programs/macrocycles/MacrocycleEditor.tsx | — | SHIPPED 2026-06-25 (2863664)
CO12 | Coach | Individual client overview (/coach/clients/:id) | Retire the redundant Progress tab (its CoachNutritionGraphs already lives in Nutrition->History; its VolumeChart already lives in Workouts). 8 sections -> 7. Promote a compact phase-scoped weight-trend card onto Nutrition->Overview so the line is visible without drilling into History. Deep links to ?tab=progress degrade to default via the existing unknown-slug guard. | Removes a duplicate page; surfaces the weight trend one fewer click away. Simplify + avoid redundant pages. | P2 | S | src/components/client-overview/sections.ts; ClientOverviewTabs.tsx; ClientOverviewNav.tsx; tabs/NutritionTab.tsx; nutrition/PhaseWeightTrendCard.tsx (new); tabs/ProgressTab.tsx (deleted) | Linear; Notion (consolidated detail views) | SHIPPED 2026-06-25 (39050a3); coach live-verify pending
CO13 | Coach | Coach surfaces (polish pass) | Live-review polish: (1) weight-trend Y-domain now spans start+target so the target line is never off-chart; (2) new CoachShell wraps Coach Hub + Content Assignments so the left sidebar rail persists on those standalone pages; (3) Content Assignments empty-state copy points to Learn (was dead /educational-videos); program with no title falls back to macrocycle name then "Training program" (was "Untitled program"); (4) MetricCard hero value now font-mono+tabular app-wide; team cards equal-height + ClickableCard (was <Card onClick>). Capacity bars left as-is (load-encoded colours are intentional). | Consistency + discoverability across the coach experience; removes dead copy and a11y/card anti-patterns. | P2 | M | PhaseWeightTrendCard.tsx; useClientWorkouts.ts; coach/CoachShell.tsx (new); coach/teams/TeamCard.tsx; ui/metric-card.tsx; pages/coach/CoachHub.tsx; pages/coach/CoachContentAssignments.tsx | Linear; Height | SHIPPED + LIVE-VERIFIED 2026-06-25 (162155f)
DS1 | Global | Design foundation (typography + card primitive) | App-wide foundation pass to close the gap between mockups and the live UI: (1) swap body typeface DM Sans -> Geist (index.html link + tailwind sans token); (2) flatten the Card primitive -- drop shadow-sm so cards sit flat with a hairline border instead of the stock shadcn float; (3) cap font-bold at 600 via tailwind fontWeight theme override (every 700 header -> crisp 600 in one place); (4) CardTitle 600 -> 500. Bebas Neue display headlines + JetBrains Mono numerals unchanged. | Mockups read more premium than the site due to heavy 700 weights + shadowed stock-shadcn cards + generic font. Foundation-level fix lifts every page (client/coach/public/admin) at once. | P2 | M | index.html; tailwind.config.ts; src/components/ui/card.tsx | Linear; Vercel/Geist; Anthropic design system | SHIPPED + LIVE-VERIFIED 2026-06-26 (coach dashboard + client overview + public /services)
WK13 | Workout | Program board + coach calendar | Move session to another day: board kebab 'Move to day' (dated start-anchored picker) + 'apply to following weeks?' cascade prompt + coach-calendar move via move_plan_session RPC (1:1 clones only; team-shared rejected -> 'edit from the team board') | Coaches adjust a client schedule without rebuilding weeks; the one net-new board affordance from the redesign (B4/B5 tails) | P1 | M | MuscleBuilderPage/SessionBlock/MobileDayDetail/ClientScheduleCalendar + move_plan_session RPC |  | SHIPPED + LIVE-VERIFIED 2026-07-02 (spec docs/DAY_MOVE_SLICE_BUILD.md). 3 smoke-found anchor-label bugs fixed same day (picker off-by-one, toast copy, mobile day-strip) - LESSON: all board weekday labels derive from assignment-start anchor, never Mon-first. Follow-up (merged 7ee0f02): copy/paste-day + remove-muscle toasts anchored too.
MS4 | Messaging | Contextual comments | Per-object comment threads on a logged session / weekly check-in / nutrition adjustment (coach<->client two-way), distinct from general chat and care-team messages | Feedback lives where it's relevant ('great pressing' on THE session); closes the redesign doc's B6 - last increment of COACH_CLIENT_REDESIGN.md | P1 | M | contextual_comments table + trigger + ContextualCommentThread; mounts: SessionLogViewer/NutritionCheckInCard/NutritionAdjustmentWeekCard/ClientNutritionProgress |  | SHIPPED + LIVE-VERIFIED 2026-07-03/04 (spec docs/B6_CONTEXTUAL_COMMENTS_BUILD.md; migration 20260703120000). RLS matrix + ownership trigger DB-proven; two-way check-in thread live; author names via get_coach_for_client (NOT coaches_client_safe - RLS-broken for clients). REMAINING fast-follows: client-side session+adjustment threads (no host surface yet), unread badges/notifications.
UN1 | Cross-cutting / Identity | Messaging + Account/Profile (cross-role) | Introduce a user-chosen username/handle as the cross-role DISPLAY identity. Show it as the sender name in coach<->client messages and wherever a name renders across roles. Settable in account settings (and/or onboarding); unique + reserved-word handling; backfill/default for existing users; exposed via an RLS-safe client-readable path so both roles can resolve it. | Client message view shows the coach as "Someone" today -- sender names resolve only from profiles_public, which a client cannot read for a coach (coaches live in coaches/coaches_public). A username is a shareable, RLS-safe, stable identity that removes per-surface name-resolution hacks. | P1 | M | src/components/messaging/CoachClientThread.tsx (sender resolve ~L138); profiles/coaches schema (new username col); account settings; get_coach_for_client (interim) |  | SHIPPED + COWORK-VERIFIED ON PROD 2026-07-05 (commit 4a1a9dc, migration 20260706173434, bundle index-CAjo31y9). DB PROVEN via jwt-impersonation: cross-role fix = as the client, direct profiles_public read of the coach returns 0 rows (RLS) BUT get_public_identities returns the coach username "hasandashti3" -- the exact Someone gap closed. set_username rejects reserved ("That username is reserved") + case-insensitive taken ("taken") + valid succeeds {ok:true}; anon->42501 on the resolver. Backfill: 0 null / 0 case-insensitive dup / 0 reserved (coach=hasandashti3, +online=hdx1). UI account settings (/account): @ Username card renders -- helper "public handle, shown as your name in messages, letters/numbers/underscores 3-20", @-prefixed input w/ current handle, Save. MESSAGE-RENDER SMOKE PASSED 2026-07-05: seeded a coach msg, viewed as +online client -> sender rendered the coach USERNAME ("DrIron", after Hasan changed it from backfill hasandashti3 via the account-settings field = SET path also confirmed), NOT "Someone", NOT display_name ("Hasan Dashti"). Full end-to-end pass. Phase 2 (noted, not built): care-team/coach-cards/onboarding.
BUG12 | Navigation / bug | Top navbar user Menu (desktop DropdownMenu) | Desktop nav user-menu wont open when the page is scrolled -- opening it appears to collapse; user must scroll to top to use it. Fix: set modal={false} on the DropdownMenu in Navigation.tsx (~L463). | Root cause (Cowork-diagnosed live 2026-07-05): the Radix DropdownMenu is modal by default -> on open it applies react-remove-scroll scroll-lock which mutates body/html overflow and BREAKS the sticky nav (position:sticky top:0). DOM-proven: menu open -> nav.top=-600 (off-screen, scrollY 600) + body scroll-locked + the menu IS open but anchored off-screen; menu closed -> nav.top=0 sticky OK. So the menu opens off-screen = looks collapsed. | P1 | XS | src/components/Navigation.tsx ~L463 (DropdownMenu -> modal={false}) |  | FIXED + COWORK-VERIFIED ON PROD 2026-07-05 (commit dc7ca65, bundle index-mKrveo4n). modal={false} on Navigation.tsx desktop DropdownMenu. DOM-proven: scrolled 1200px, open Menu -> nav stays sticky top:0 (was -600), dropdown open + ON-SCREEN (top:56, anchored to trigger), no body scroll-lock; visually confirmed dropdown renders (Role/Dashboard links/Account/Sign Out); Escape closes cleanly, nav stays sticky. Bug (menu opening off-screen when scrolled) resolved.
CC10 | Cross-cutting | Error states | Add a visible error branch to every data surface; stop degrading fetch failures into empty/placeholder states. Bundle with CC6 (same ~53 files) -- one pass = layout-shaped skeleton + error branch per surface. | SYSTEMIC: 0 of 16 audited shipped surfaces have a visible error branch. Actively misleading -- CoachAlerts.tsx:96 shows "0 alerts" on fetch fail; MeetOurTeam:76 shows "team being assembled" on a blip; TestimonialsList:87 falls back to 3 FAKE 5-star cards; CoachPublicPage:98 collapses errors+404. Contradicts CLAUDE.md {error} destructure-and-throw (Client Overview tabs swallow it: NutritionTab:86, CareTeamTab:115, SessionsTab:111, OverviewTab:119, ProfileInfoTab:100). | P1 | M | coach/CoachAlerts.tsx:96, pages/MeetOurTeam.tsx:76, marketing/TestimonialsList.tsx:87, pages/CoachPublicPage.tsx:98, client-overview/tabs/* | — | OPEN (new, CC 2026-07-12). Highest new-item priority; sequence above CT1. Cheap: error var + branch per surface. SPEC: DESIGN_UPGRADE_SPECS_BATCH2_2026-07-12.md.
CC9 | Cross-cutting | A11y / ClickableCard | Replace 13 <Card onClick> with <ClickableCard> (role=button/tabIndex/Enter-Space/focus ring). Also AlertsCard.tsx:70 onClick on <Alert>. | CLAUDE.md mandates ClickableCard; 13 sites bypass it -> keyboard-inaccessible nav/action cards. | P1 | S | client/QuickActionsGrid.tsx:50, coach/CoachAlerts.tsx:113/129/145, admin/AdminMetricsCards.tsx:205, admin/AdminBillingManager.tsx:554, admin/SiteContentManager.tsx:166, client/ClientDashboardLayout.tsx:736, coach/CoachClientDetail.tsx:497, coach/programs/ProgramEditor.tsx:431, coach/programs/macrocycles/MacrocycleEditor.tsx:549, pages/ClientSubmission.tsx:222, pages/coach/CoachTrainingDashboard.tsx:289/328, client/AlertsCard.tsx:70 | ui/clickable-card.tsx pattern | OPEN (new, CC 2026-07-12).
DS2 | Cross-cutting | Flat surfaces | Extend PUB8 flatten to authed shells: remove bg-gradient-to-br page washes (admin/client/auth), retire surviving gradient button (PaymentStatusDashboard:732), replace gradient-clipped hero numbers (CalorieResults:47/90, AdjustmentCalculator:641) with flat Bebas crimson, drop from-primary-to-accent icon medallions. | PUB8/BTN1 flattened public pages; admin/client/auth shells never got the pass -> pre-flatten gradient signature persists on authed surfaces. Gradient-clipped hero numbers directly contradict the Bebas-flat-crimson bar. | P2 | M | admin/AdminPageLayout.tsx:87, admin/AdminDashboardLayout.tsx:151, pages/WorkoutLibrary.tsx, pages/EducationalVideos.tsx, pages/BillingPayment.tsx, pages/PaymentStatus.tsx, pages/PaymentReturn.tsx, Auth/ResetPassword/EmailPending/EmailConfirmed/NotFound/Unauthorized/CoachSignup/CoachPasswordSetup, calculator/CalorieResults.tsx, calculator/AdjustmentCalculator.tsx, PaymentStatusDashboard.tsx:732 | PUB8 flatten precedent | OPEN (new, CC 2026-07-12).
DS3 | Cross-cutting | Shadow discipline | Remove caller-added shadows (46 sites outside ui/). RULING LOCKED 2026-07-12: CHANGE THE PRIMITIVE -- swap clickable-card.tsx:52 hover:shadow-md for a border/bg hover so ClickableCard obeys the flat bar (fixes ~26 call sites at source). | Card primitive is correctly flat (ui/card.tsx:6) but callers re-add shadow-lg/md, and the sanctioned ClickableCard violates the no-shadow bar at source. | P2 | S | ui/clickable-card.tsx:52, PaymentStatusDashboard.tsx:463/477/502, coach/CoachAlerts.tsx:114/130/146, client/QuickActionsGrid.tsx:52, admin/AdminMetricsCards.tsx:207, ProgramLibrary.tsx:565, +~35 more (CC scan) | — | OPEN (ruling locked: change primitive) (new, CC 2026-07-12). See design-owner decision doc.
CC11 | Cross-cutting | i18n / RTL | i18n + RTL pass on shipped/public surfaces: add useTranslation where missing; swap physical mr-/ml-/left-/pl- for logical me-/ms-/start/ps- so Arabic dir-flip works. | App is en/ar with dir flip. Public surfaces have hardcoded English (MeetOurTeam ~9 strings, Testimonials, TestimonialsList no useTranslation) + physical-direction classes (search icons wrong side in Arabic: TestimonialsManager:283, CoachMyClientsPage:1003; NutritionPhaseCard:184/225/231). CoachPublicProfile headline flows untranslated into the SEOHead title. | P2 | M | pages/MeetOurTeam.tsx, pages/Testimonials.tsx, marketing/TestimonialsList.tsx, nutrition/NutritionPhaseCard.tsx:184/225/231, coach/CoachSessions.tsx, client-overview/tabs/NutritionTab.tsx:243/326, coach/CoachPublicProfile.tsx:61 | — | OPEN (new, CC 2026-07-12).
MS5 | Messaging | Mobile dock | Give coach + admin mobile docks a Messages item with an unread badge (client dock already has it). Reuse useStaffUnreadCounts / get_unread_message_counts_for_staff (already consumed in CoachMyClientsPage). | MS2 shipped on the client dock only; coach/admin docks have no Messages item -> a coach/admin on mobile has no dock-level unread signal. | P2 | S | App.tsx:154-224, coach/CoachSidebar.tsx:232, admin/AdminSidebar.tsx:131, hooks/useStaffUnreadCounts | — | OPEN (new, split from MS2, CC 2026-07-12).
PUB11 | Public / Marketing | Coach page SEO | Add Schema.org AggregateRating/Review JSON-LD to CoachPublicPage (deferred in T2 to T1; T1 never built it -- zero ld+json in src today). | Orphaned deferral + real SEO miss on a page whose whole point is reputation; the rating aggregate is already fetched (CoachPublicPage:90-91,201-203), just not marked up. | P2 | S | pages/CoachPublicPage.tsx, components/SEOHead.tsx | — | OPEN (new, CC 2026-07-12).
BUG13 | Sessions | Client visibility | Coach-created direct_calendar_sessions never render on the client side (client /sessions reads session_bookings only). Surface them to clients, or fold direct sessions into the booking model (see SE1 decision). | RLS permits client SELECT on direct_calendar_sessions but no client code reads it (only SessionsTab.tsx:82 + DirectClientCalendar.tsx:93, both coach). Coach schedules a session; the client never sees it. Live bug, not a design nicety. | P1 | M | pages/ClientSessions.tsx, client-overview/tabs/SessionsTab.tsx:82, coach/programs/DirectClientCalendar.tsx:93 | — | OPEN (new, CC 2026-07-12). Tied to the SE1 architecture decision. SE1 model locked to session_bookings -> surfacing coach direct sessions likely folds into that unification.

## Mobbin Screen Links
Exact Mobbin references (pulled via the Mobbin MCP)
Topic | Supports row(s) | Source | What it shows | Open in Mobbin
Coach roster & client detail | CO5, CO6, CO7 | Intercom (web) | Three-pane: saved Views with counts -> conversation list -> collapsible context panel (Lead data / notes / tags / segments) | Open screen ->
Coach roster | RO1, RO3 | Intercom (web) | Unassigned inbox: scannable rows + Filter control | Open screen ->
Coach roster | RO1, RO2, CO5 | Front (web) | Shared inboxes with team views + per-view counts | Open screen ->
Coach roster (mobile) | RO1, CO1 | Deel (ios) | Mobile roster: 'AT RISK' badge + status-count tiles (Draft / Invited / Active) - closest mobile analogue to IGU's Action-needed/Drifting | Open screen ->
Coach product (fitness) | CO1-CO8 | Hevy Coach (ios) | Rare fitness coach-side reference: coach dashboard preview + per-client-count pricing | Open screen ->
Workout logging | WK1, WK2, WK4 | Hevy (ios) | Per-exercise rest timer, SET/PREVIOUS/KG/REPS columns, set-completion checkmarks | Open screen ->
Workout logging | WK4, WK5 | Hevy (ios) | Warmup 'W' rows + previous performance as ghost values | Open screen ->
Workout logging | WK3 | Hevy (ios) | Add Exercise / Settings / Discard Workout controls | Open screen ->
Workout logging | WK1, WK4 | Ladder (ios) | 'Log It' per-set Effort% + completion checkmarks + View History | Open screen ->
Exercise detail | HX1 | Fitbod (ios) | Projected 1-Rep-Max line chart + Weight / Volume / Repetition records + Exercise History | Open screen ->
Exercise detail | HX1, HX2 | Tonal (ios) | Strength / Power / Volume tabs, 1RM chart + per-set history with 1RM column | Open screen ->
Exercise detail | HX1 | Hevy (ios) | Summary / History tabs, muscle map, Heaviest Weight / 1RM / Best Set chart toggle | Open screen ->
Exercise history | HX2 | Ladder (ios) | History table: Date / Equipment / Effort / Reps / 1RM | Open screen ->
Weight trend | NU1 | Fitbit (ios) | Two series: raw 'Weight' vs 'Your Weight Trend' - the exact scatter-vs-trend pattern in NU1 | Open screen ->
Weight trend | NU1, NU5 | MacroFactor (ios) | Scale Weight trend + average / difference + 1W..All timeframe toggle | Open screen ->
Weight trend | NU1, NU5 | MyFitnessPal (ios) | Progress: start / current / change % + trend line + entries list | Open screen ->
Weight goal viz | NU2, NU3 | Noom (ios) | Predictive goal curve to a target date | Open screen ->
Landing pricing | PUB2 | Programa (site) | 3-tier with highlighted 'Recommended Plan' + per-card CTA | Open screen ->
Landing pricing | PUB2 | Homerun (site) | 'Most popular' middle plan + locked / unlocked feature rows | Open screen ->
Landing pricing | PUB2 | Cursor (site) | Clean 4-tier with 'Recommended' + Monthly / Yearly toggle | Open screen ->
Landing pricing | PUB2 | Mural (site) | 'Most popular' bordered highlight across 4 plans | Open screen ->
Landing hero | PUB1, PUB4 | Framer 'BLOK' (site) | Fitness-studio hero: bold headline + subhead + CTA + testimonial card | Open screen ->
Landing hero | PUB1 | ClassPass (site) | Category hero with image + single CTA | Open screen ->
Landing hero | PUB1 | Squarespace (site) | 'Start a free trial today / No credit card required' hero | Open screen ->
Landing hero | PUB1 | Superpower (site) | Dark dramatic hero with one prominent CTA | Open screen ->