IGU

Intensive Gainz Unit

Build-Out & Hiring Action Plan

Roles, finances, agreements & sequencing toward launch

Prepared for Hasan  •  June 2026

Target public launch: 12 July 2026

Working draft — not legal or financial advice. Confirm all Kuwait-law specifics with a licensed local lawyer and accountant.

# Contents

# 1. Where IGU stands today

IGU is a sole establishment licensed for sports consultation services in Kuwait — legally, the business is you, Hasan. The coaching platform is built and in pre-launch, with payments (Tap), client onboarding, PAR-Q medical screening, and a working coach/dietitian compensation engine already live. Public launch is targeted for 12 July 2026.

You want to staff up: an in-house coaching team (IGU-approved, following IGU guidelines), software/finance/ops support, and a referral relationship with dietitians and physios. You intend to keep ownership for now, but are open to sharing part of the profits with key contributors. This document is the master action list — what needs doing, why it matters, and in what order — across every aspect of standing the business up properly.

# 2. Three structural facts that shape everything

A. Sole establishment = unlimited personal liability There is no corporate veil. Business debts and claims — including a coach's advice given under IGU's name — can reach your personal assets. Consequences: airtight scope-of-practice and liability clauses in every staff/partner contract, professional liability insurance, and a planned path to a WLL once revenue justifies the cost.

B. Your licence is your guardrail Coaching fits squarely inside a sports-consultation licence. Nutrition (dietitians) and physiotherapy are regulated health activities that very likely fall OUTSIDE it. Plan: keep coaches in-house under IGU; treat dietitians and physios as independent, separately-licensed referral partners who carry their own clinical liability. Verify exact scope with your licence authority before hiring either in-house.

C. You can't issue equity in a sole establishment There are no shares to give. For anyone you want as a 'partner,' the realistic tools are: (a) a profit-share / revenue-share contract (a % of defined revenue, no ownership), or (b) converting to a WLL later and granting real equity. Put any equity promise in writing as a future conversion trigger — never a verbal handshake.

# 3. Master action list by workstream

Six workstreams. Priority key: Now (start immediately), Pre-launch (before 12 Jul), Phased (scale to demand).

## A. Legal & structure

| Action | Why it matters | Priority |
| --- | --- | --- |
| Engage a Kuwaiti corporate/commercial lawyer | Everything below depends on correct entity & contract advice. This is the single first move. | Now |
| Confirm licence scope for each planned service | Determines whether dietitian/physio can ever be in-house vs referral-only. | Now |
| Confirm the establishment can sponsor the staff you plan to hire (PAM file) | You can't legally employ in Kuwait without the right activity + sponsorship capacity. | Now |
| Decide entity path: stay sole vs plan WLL conversion | Drives liability protection and your ability to give real equity later. | Near-term |
| Draft template agreements (see §5) | Reusable contracts for every hire type; nothing signed without them. | Pre-launch |
| Finalise client-facing legal: Terms, Privacy, PAR-Q waiver, refund policy | You hold health data and give fitness advice — assumption-of-risk & disclaimers are essential. | Pre-launch |
| Confirm health-data (PHI) handling meets Kuwait requirements | PAR-Q + intake data is sensitive; mishandling is a liability and trust risk. | Pre-launch |
| Put professional liability / indemnity insurance in place | Backstops the personal-liability exposure of a sole establishment. | Near-term |

## B. Finance & accounting

| Action | Why it matters | Priority |
| --- | --- | --- |
| Open a dedicated business bank account | Separate business from personal money — basic hygiene and audit-ability. | Now |
| Engage an outsourced accountant / bookkeeper | Clean books, invoicing, Tap reconciliation, gratuity tracking from day one. | Now |
| Build the financial model (revenue, payroll, gratuity, ops, runway, break-even) | Turns 'who can I afford' into a number tied to client volume. | Pre-launch |
| Formalise the monthly coach/dietitian payout & disbursement process | Engine exists in-app; the actual money-out and pay schedule must be defined. | Pre-launch |
| Set a gratuity / end-of-service reserve for employees | End-of-service indemnity is a real, accruing liability under Kuwait labour law. | Ongoing |
| Decide capital plan: how much you inject + target break-even month | Sets the runway the whole hiring plan must fit inside. | Pre-launch |
| Review pricing vs market (links to §E) | Confirms tiers are competitive and margins hold. | Near-term |

## C. People & hiring

| Action | Why it matters | Priority |
| --- | --- | --- |
| Lock the launch headcount (see §4) | Hire the minimum that makes launch safe — not the full org chart. | Now |
| Recruit a lead/senior developer or dev partner | You are currently the single point of failure on a SaaS handling health data + payments. | Now |
| Write role descriptions + an IGU Coaching Standards doc | The standards become a signed annex so 'follow IGU guidelines' is enforceable. | Pre-launch |
| Recruit Head Coach + initial coaches | Head Coach owns quality and unblocks you as the bottleneck; coaches hire to demand. | Phased |
| Line up referral-partner dietitian(s) and physio(s) | Adds nutrition/physio value without taking them in-house (licence + liability). | Near-term |
| Decide partner(s) / profit-share participants & terms | Your call: who, if anyone, shares profit — and on what conditions. | Founder decision |
| Add outsourced/fractional: accountant, designer, marketing, support | Scale these to traction rather than hiring ahead of revenue. | Phased |

## D. Pricing & unit economics

| Action | Why it matters | Priority |
| --- | --- | --- |
| Validate live pricing against Kuwait competitors | Confirms the 12 / 40 / 75 / 150 / 250 KWD ladder is positioned right. | Near-term |
| Confirm per-tier operations costs are current | Only Team Plan ops (2.0 KWD) is visible; others must be verified for true margin. | Pre-launch |
| Pressure-test payout % vs take-home targets (Jr ~50 / Sr ~65 / Lead ~85) | Ensures coach pay is attractive yet leaves sustainable IGU profit. | Pre-launch |
| Reconcile the CLAUDE.md documentation drift | Doc table still says 'hourly / Head Coach 5 KWD'; live model is flat / 7 KWD. Fix the doc. | Now |
| Decide referral pricing for dietitian/physio | Sets the economics of the referral model before partners are signed. | Near-term |

## E. Market research

| Action | Why it matters | Priority |
| --- | --- | --- |
| Map Kuwait competitors & their pricing (gyms, online coaches, apps) | Grounds positioning and the pricing review. | Near-term |
| Benchmark coach compensation in the Kuwait market | Tells you whether IGU payouts attract the talent you want. | Near-term |
| Estimate addressable market + realistic month 1-6 client volumes | The revenue input the finance model needs to be real. | Near-term |
| Validate acquisition channels (align with docs/marketing.md) | Confirms where the first clients actually come from. | Pre-launch |

## F. Operations & compliance

| Action | Why it matters | Priority |
| --- | --- | --- |
| Document coach quality standards & SOPs | Consistent client experience across every IGU coach. | Pre-launch |
| Define client support process & response SLAs | Support is usually the first thing to break at scale. | Pre-launch |
| Define the medical escalation path (PAR-Q flagged → review) | A flagged client must have a clear, safe handling route. | Pre-launch |
| Set refund & dispute handling rules | Avoids ad-hoc decisions and payment disputes. | Pre-launch |
| Stand up a KPI / admin dashboard review cadence | Daily admin summary exists; turn it into a real operating rhythm. | Phased |

# 4. Roles needed for initial launch

Tiered so you hire the minimum that makes launch safe, then scale.

| Role | Engagement model | Licence / scope note | When |
| --- | --- | --- | --- |
| Lead / Senior Developer | Remote independent contractor (USD), IP assigned to you | Build role — outside service licence | Now |
| Head Coach | Employee | In scope (sports consultation) | Pre-launch |
| Coaches (Jr / Sr) | Employees, hire to demand | In scope (sports consultation) | Launch+ |
| Dietitian | Referral partner (holds own licence) | Likely OUTSIDE licence — keep referral | Near-term |
| Physiotherapist | Referral partner (holds own licence) | Regulated medical — keep referral | Post-launch |
| Accountant / Bookkeeper | Outsourced firm | N/A | Now |
| Designer / Marketing | Contractor / fractional | N/A | Phased |
| Customer support | Employee or contractor | N/A | Launch+ (with volume) |

Coaches specifically: because they are IGU-branded and must follow your guidelines, you exercise real control over how they work — which legally points to employee, not contractor. That's the right call for brand quality, but it carries gratuity obligations and means your coaching standards must be a signed annex to the contract.

# 5. Agreements everyone needs to sign

A mutual NDA plus one role-appropriate main contract covers about 90% of people. Have your lawyer produce these as reusable templates.

| Who | Agreement | Key clauses |
| --- | --- | --- |
| Coaches (employees) | Employment contract + IGU Standards annex | Scope of practice; duty to follow IGU guidelines; confidentiality; IP; end-of-service gratuity; termination; non-solicitation of IGU clients |
| Developers / designers (remote) | Independent contractor / services agreement | IP assignment to you (critical); confidentiality; explicit no-employment relationship; payment terms; deliverables |
| Dietitians / physios (referral) | Referral / partnership agreement | Partner holds own licence + clinical liability; referral terms/fees; IGU not liable for their advice; client data-sharing consent |
| Partners (profit-share) | Profit / revenue-share agreement | % and definition of revenue; no ownership; vesting or tenure condition; exit/dispute; trigger to convert to equity if a WLL is formed |
| Anyone touching client data | NDA + data-handling addendum | Confidentiality; PHI handling rules; return/destroy data on exit |
| Clients | Terms of Service + Liability Waiver + PAR-Q consent + Privacy Policy | Assumption of risk; medical disclaimer; refund policy; data-processing consent |

# 6. Recommended sequence

Order matters because later steps depend on the lawyer's answers. Roughly:

- Engage the lawyer and the accountant (week 1). Everything keys off this.

- Lawyer confirms licence scope, sponsorship capacity, and entity path; begins drafting template agreements.

- Open the dedicated business bank account.

- Lock launch headcount and start recruiting the developer (run in parallel with the legal work).

- Build the financial model; set your capital injection and target break-even month.

- Run market research; validate pricing and coach compensation against it.

- Finalise the IGU Coaching Standards doc and coach onboarding/approval flow.

- Sign agreements; line up referral dietitian(s) and physio(s).

- Put professional liability insurance in place.

- Launch (12 July 2026).

The one thing to do this week Engage a Kuwaiti corporate/commercial lawyer and brief them with §2 and the question list in Appendix B. Almost every other decision — entity, who you can hire, what contracts say, whether dietitian/physio can be in-house — flows from their answers.

# Appendix A. Current pricing & compensation (live in the platform)

Pulled from the live model (supabase/migrations/20260327_flat_payout_model.sql). All figures KWD per client per month. Coach/dietitian payouts are flat by professional level (Junior / Senior / Lead).

## Service tiers & monthly price

| Tier | Price | Coach payout (Jr / Sr / Lead) | Dietitian payout (Jr / Sr / Lead) |
| --- | --- | --- | --- |
| Team Plan | 12 | Head Coach flat 7 | — |
| 1:1 Online | 40 | 20 / 26 / 34 | — |
| 1:1 Complete | 75 | 20 / 26 / 34 | 15 / 20 / 20 |
| Hybrid | 150 | 60 / 80 / 105 | 15 / 20 / 20 |
| In-Person | 250 | 105 / 140 / 185 | 15 / 20 / 20 |

## Indicative IGU gross margin (Junior level, before per-tier ops cost)

| Tier | Price | Coach | Dietitian | Gross before ops |
| --- | --- | --- | --- | --- |
| Team Plan | 12 | 7 | — | 5.0 (ops 2.0 → 3.0 profit) |
| 1:1 Online | 40 | 20 | — | 20.0 |
| 1:1 Complete | 75 | 20 | 15 | 40.0 |
| Hybrid | 150 | 60 | 15 | 75.0 |
| In-Person | 250 | 105 | 15 | 130.0 |

## Guardrails enforced by the payout engine

- Minimum IGU profit: 3 KWD on Team/Online, 5 KWD on premium tiers — a subscription is blocked if violated (admin can override).

- Maximum discount: 30%, applied proportionally across coach, dietitian and IGU — operations costs are never discounted.

- Level restrictions: Lead Coach blocked from 1:1 Online; Lead+Lead blocked from 1:1 Complete (margin would breach the minimum).

- Take-home targets: Junior ~50%, Senior ~65%, Lead ~85% of the client price.

Note on data freshness Per-tier operations costs are only confirmed for Team Plan (2.0 KWD). The other tiers' ops costs live in the igu_operations_costs table and should be pulled live before the finance model treats any margin as final. These rates are not fixed — you said they're fully open to adjustment. The finance model is where we test alternatives.

# Appendix B. Questions to bring to the lawyer

- Can my sole establishment, under its current sports-consultation activity, sponsor and employ coaches? What activities/permits would I need to add?

- Do in-house dietitian or physiotherapy services require separate Ministry of Health licensing, or a different entity? Can I offer them at all under IGU as it stands?

- If dietitians/physios are referral partners holding their own licences, what does IGU need in the agreement to be clearly NOT liable for their clinical advice?

- Given unlimited personal liability, at what point should I convert to a WLL, and what does that process and cost look like?

- Are coaches who follow my mandated guidelines legally employees rather than contractors? What are my gratuity and end-of-service obligations?

- Can a profit-share agreement be enforceable without granting ownership in a sole establishment? How should an equity-on-conversion promise be written?

- What client-facing legal documents (Terms, Privacy, liability waiver, PAR-Q consent) do I need, and what does Kuwait law require for handling client health data?

- What are the rules for engaging remote international contractors (developers/designers) — any withholding, registration, or contract requirements on my side?